## Final Submittal
SUBMITTAL REGISTER |  |  |  |  | TITLE AND LOCATION: | [23 empty] | PROJECT DATE: (MONTH/YEAR)
A/E Project Number:
Activity No. | Transmittal No. | Section Number | Paragraph Number | Description of Submittal | 01-PRECON SUBMITTALS | 02-SHOP DRAWINGS | 03-PRODUCT DATA | 04-WARRANTIES | 05-SAMPLES | 06-DESIGN DATA | 07-TEST REPORTS | 08-CERTIFICATES | 09-MFRS INSTRUCTIONS | 10-MFRS FIELD REPORT | 11 -PROJECT RECORD DOCUMENTS | 12-O&M DATA | 13-LEED / SUSTAINABLE | 14-CLOSEOUT SUBMITTALS | Information Only | A/E Approval G, AE | Government Approved G, AO | Submit | Approval Needed By | Scheduled Submittal Date | Action Code | Date of Action | Action Code | Date of Action
CONTRACT MODIFICATION PROCEDURES
|  | 01 26 00 | 1.3 | Contract Modification Procedures | X | [15 empty] | X
ADMINISTRATIVE REQUIREMENTS
|  | 01 30 00 | 1.1 | Substitutions | X |  | X |  | X | [11 empty] | X
|  | 01 30 00 | 1.11 | Requests for Information | [10 empty] | X |  |  |  | X
|  | 01 30 00 | 1.12 | Project Meeting Minutes | [10 empty] | X | [5 empty] | X
|  | 01 30 00 | 1.13 | Project Register | [10 empty] | X | [5 empty] | X
|  | 01 30 00 | 1.14 | Contractor Production Reports | [10 empty] | X | [5 empty] | X
|  | 01 30 00 | 1.15 | Record Photographs | [10 empty] | X | [5 empty] | X
CONSTRUCTION PROGRESS DOCUMENTATION
|  | 01 32 16 | 1.5 | Preliminary Project Schedule | X | [15 empty] | X
|  | 01 32 16 | 1.6 | Phasing Schedule (Add/Alter Projects) | X | [15 empty] | X
|  | 01 32 16 | 1.7 | Project Schedules and Requirements for Maintaining Progress | X | [15 empty] | X
|  | 01 32 16 | 1.7M | Changes | [10 empty] | X | [5 empty] | X
|  | 01 32 16 | 1.8 | Short Interval Schedules | [10 empty] | X |  |  |  | X
PHASED CONSTRUCTION
|  | 01 32 16.10 | 1.14 | Phasing Schedule (Add/Alter Projects) | X | [15 empty] | X
SUSTAINABLE DESIGN REPORTING
|  | 01 33 29 | 1.3D | Sustainable Design Action Plans | [12 empty] | X |  | X
|  | 01 33 29 | 1.3E | Sustainable Design Progress Reports | [9 empty] | X |  |  | X |  | X
|  | 01 33 29 | 1.3F | Sustainable Design Documentation Submittals |  |  | X | [9 empty] | X |  | X
GOVERNMENT SAFETY REQUIREMENTS
|  | 01 35 26 | 1.4B | Fire Prevention Plan | X | [5 empty] | X | X | [8 empty] | X
|  | 01 35 26 | 1.5C | Safety Plan | X | [5 empty] | X | X | [8 empty] | X
|  | 01 35 26 | 1.6 | Security Plan | X | [5 empty] | X | X | [8 empty] | X
ENVIRONMENTAL PROCEDURES FOR REFRIGERANTS
|  | 01 35 43.19 | 1.3 | Refrigerant log book | [13 empty] | X |  |  | X
INDOOR AIR QUALITY PROCEDURES
|  | 01 35 46 | 1.3A | Supplementary Condition Schedule | X |  | X | [13 empty] | X
|  | 01 35 46 | 1.3B | Material safety data sheets |  |  | X | [13 empty] | X
QUALITY CONTROL
|  | 01 45 00 | 1.3 | Quality Control Plan | [10 empty] | X | [5 empty] | X
|  | 01 45 00 | 1.3 | Complete Submittal Register and Schedule | [10 empty] | X | [5 empty] | X
|  | 01 45 00 | 1.3 | Quality Control Report | [10 empty] | X |  |  |  | X
|  | 01 45 00 | 1.3 | Testing Plan and Log | [10 empty] | X |  |  |  | X
|  | 01 45 00 | 1.3 | Monthly summary report of field tests | [10 empty] | X |  |  |  | X
|  | 01 45 00 | 1.3 | QC Meeting Minutes | [10 empty] | X |  |  |  | X
|  | 01 45 00 | 1.3 | Rework items list | [10 empty] | X |  |  |  | X
|  | 01 45 00 | 1.3 | QC Certifications | [10 empty] | X |  |  |  | X
|  | 01 45 00 | 1.3 | QC Punch List | [10 empty] | X |  |  |  | X
TEMPORARY FACILITIES AND CONTROLS
|  | 01 50 00 | 1.4D.1 | Temporary Utilities Plan | X | [15 empty] | X
|  | 01 50 00 | 1.5B | Temporary Support Facilities Plan | X | [15 empty] | X
|  | 01 50 00 | 1.5D.4 | Temporary Administration Trailer | X | [15 empty] | X
|  | 01 50 00 | 1.6B | Temporary Security and Protection Plan | X | [15 empty] | X
TEMPORARY TREE AND PLANT PROTECTION
|  | 01 56 39 | 1.3A | Product Data | X |  | X | [13 empty] | X
|  | 01 56 39 | 1.3B | Qualification Data | X | [6 empty] | X | [8 empty] | X
|  | 01 56 39 | 1.3C | Certification | [7 empty] | X | [6 empty] | X
|  | 01 56 39 | 1.3D | Maintenance Recommendations | [11 empty] | X |  |  | X
CLOSEOUT PROCEDURES
|  | 01 77 00 | 1.3 | Maintenance Manuals | [13 empty] | X |  |  | X
|  | 01 77 00 | 1.4 | Instruction Certificate | [13 empty] | X |  |  | X
|  | 01 77 00 | 1.5 | Warranties | [13 empty] | X |  |  | X
|  | 01 77 00 | 1.6B | Record Drawings | [13 empty] | X |  |  | X
|  | 01 77 00 | 1.6D | Record Specifications | [13 empty] | X |  |  | X
|  | 01 77 00 | 1.8B | QC Punch List | [13 empty] | X |  |  | X
|  | 01 77 00 | 1.8C | Equipment List | [13 empty] | X |  |  | X
|  | 01 77 00 | 1.9 | Real Property Records | [13 empty] | X |  |  | X
DEMONSTRATION AND TRAINING
|  | 01 79 00 | 1.2A | Instruction Program and Manuals | [11 empty] | X |  |  |  |  | X
|  | 01 79 00 | 1.2B | Qualification Data for instructor | [11 empty] | X |  |  |  |  | X
|  | 01 79 00 | 1.2C | Attendance Record for each training module | [11 empty] | X |  |  |  |  | X
|  | 01 79 00 | 1.2D | Evaluations for each participant | [11 empty] | X |  |  |  |  | X
|  | 01 79 00 | 1.2E | Demonstration and Training videotapes | [11 empty] | X |  |  |  |  | X
GENERAL COMMISSIONING REQUIREMENTS
|  | 01 91 13 | Append A | Commissioning Plan | X | [12 empty] | X |  |  | X
|  | 01 91 13 | 3.3 | Start-Up Text Reports | [6 empty] | X | [6 empty] | X
|  | 01 91 13 | 3.3 | Pre-Functional Test Reports | X | [12 empty] | X |  |  | X
|  | 01 91 13 | 3.5 | Functional Test Reports | [6 empty] | X | [6 empty] | X |  |  | X
DEMOLITION
|  | 02 41 00 | 1.2A | Site Plan | X | [15 empty] | X
|  | 02 41 00 | 1.2B | Demolition Plan | X | [15 empty] | X
|  | 02 41 00 | 1.2C | Proposed Protection Measures | X | [15 empty] | X
|  | 02 41 00 | 1.2D | Record locations of capped and active utilities and subsurface construction | [13 empty] | X |  |  | X
|  | 02 41 00 | 1.2E | Warranties | [13 empty] | X |  |  | X
LIGHTING BALLAST AND LAMP DISPOSAL
|  | 02 84 16 | 1.4A | Certificates | [7 empty] | X | [7 empty] | X
|  | 02 84 16 | 1.4B | Field Test Reports | [6 empty] | X | [8 empty] | X
CAST-IN-PLACE CONCRETE
|  | 03 30 00 | 1.4 A | Data for Admixtures, vapor retarders, and slab treatments. |  |  | X | [12 empty] | X
|  | 03 30 00 | 1.4 B | LEED documentation for recycled content | [12 empty] | X |  | X
|  | 03 30 00 | 1.4 C | Design mixtures for each concrete mix | [5 empty] | X | X | [8 empty] | X
|  | 03 30 00 | 1.4 D | Statement of material content and proportions | [7 empty] | X | [7 empty] | X
|  | 03 30 00 | 1.4 E | Detail fabrication, bending, and placement of steel reinforcement. |  | X | [13 empty] | X
|  | 03 30 00 | 1.4 F | Vapor retarder |  |  |  |  | X | [10 empty] | X
|  | 03 30 00 | 1.4 G | Field Quality Control Tests and Inspection Reports | [6 empty] | X | [8 empty] | X
|  | 03 30 00 | 1.4 H | ACI 301 Sections 1 through 5 |  |  |  | X | [11 empty] | X
|  | 03 30 00 | 1.4 I | Special Inspection Reports | [6 empty] | X | [8 empty] | X
|  | 03 30 00 | 1.4 J | Saw cutting system |  |  | X | [12 empty] | X
|  | 03 30 00 | 1.4 K | Qualification Data | [7 empty] | X | [7 empty] | X
INSULATED FREEZER FLOORS
|  | 03 30 50 | 1.2 B | Data for insulation and vent piping materials |  |  | X | [12 empty] | X
INTERIOR CONCRETE SLAB REPAIRS AND JOINT FILLER REPLACEMENT
|  | 03 35 40 | 1.2 A | For each type |  |  | X | [12 empty] | X
|  | 03 35 40 | 1.2 B | Qualification Data | [7 empty] | X | [7 empty] | X
POLISHED CONCRETE FLOOR FINISHING FOR EXISTING FACILITIES
|  | 03 35 40 | 1.4 A | For each type |  |  | X | [12 empty] | X
|  | 03 35 40 | 1.4 B | Qualification Data | [7 empty] | X | [7 empty] | X
|  | 03 35 40 | 1.4 C | Pre-Certified Installers | [7 empty] | X | [7 empty] | X
POLISHED CONCRETE FLOOR FINISHING FOR NEW CONSTRUCTION
|  | 03 35 43 | 1.4 A | For each type |  |  | X | [12 empty] | X
|  | 03 35 43 | 1.4 B | Qualification Data | [7 empty] | X | [7 empty] | X
|  | 03 35 43 | 1.4 C | Pre-Certified Installers | [7 empty] | X | [7 empty] | X
POLISHED CONCRETE OVERLAY
|  | 03 35 44 | 1.4 A | For each type |  |  | X | [12 empty] | X
|  | 03 35 44 | 1.4 B | Qualification Data | [7 empty] | X | [7 empty] | X
|  | 03 35 44 | 1.4 C | Pre-Certified Installers | [7 empty] | X | [7 empty] | X
PRECAST ARCHITECTURAL CONCRETE
|  | 03 45 00 | 1.4 A | For each type of product |  |  | X | [12 empty] | X
|  | 03 45 00 | 1.4 B | LEED documentation for recycled content and regional materials | [12 empty] | X |  | X
|  | 03 45 00 | 1.4 C | Design mixtures for each concrete mix | [5 empty] | X | X | [8 empty] | X
|  | 03 45 00 | 1.4 D | Detail fabrication of precast architectural concrete |  | X | [13 empty] | X
|  | 03 45 00 | 1.4 E | For each type |  |  |  |  | X | [10 empty] | X
|  | 03 45 00 | 1.4 F | Welding certificates | [7 empty] | X | [6 empty] | X
|  | 03 45 00 | 1.4 G | Material certificates | [7 empty] | X | [6 empty] | X
|  | 03 45 00 | 1.4 H | Installaer Qualfications | [7 empty] | X | [7 empty] | X
|  | 03 45 00 | 1.4 I | Fabricator Qualifications | [7 empty] | X | [7 empty] | X
|  | 03 45 00 | 1.4 J | Special Inspector Qualifications | [7 empty] | X | [7 empty] | X
|  | 03 45 00 | 1.4 K | Special Inspection Reports | [6 empty] | X | [8 empty] | X
|  | 03 45 00 | 1.4 L | Test Reports | [6 empty] | X | [8 empty] | X
TILT-UP CONCRETE
|  | 03 47 13 | 1.3 A | For each type of product |  |  | X | [12 empty] | X
|  | 03 47 13 | 1.3 B | LEED documentation for recycled content and mixtures | [12 empty] | X |  | X
|  | 03 47 13 | 1.3 C | Design mixtures for each concrete mix | [5 empty] | X | X | [8 empty] | X
|  | 03 47 13 | 1.3 D | Detail fabrication of tilt-up concrete |  | X | [13 empty] | X
|  | 03 47 13 | 1.3 E | Material certificates | [7 empty] | X | [6 empty] | X
|  | 03 47 13 | 1.3 F | Special Inspection Reports | [6 empty] | X | [8 empty] | X
UNIT MASONRY
|  | 04 20 00 | 1.5 A | Reinforcing Steel |  | X | [13 empty] | X
|  | 04 20 00 | 1.5 B | LEED documentation for recycled content and regional materials | [12 empty] | X |  | X
|  | 04 20 00 | 1.5 C | Masonry Units and Face Brick, cementitious materials, reinforcing bars, joint reinforcement, misc anchors, ties, and metal accessories | [7 empty] | X | [7 empty] | X
|  | 04 20 00 | 1.5 D | For each type and color masonry and brick and precast items |  |  |  |  | X | [10 empty] | X
|  | 04 20 00 | 1.5 E | For each type mortar and grout | [5 empty] | X | [9 empty] | X
|  | 04 20 00 | 1.5 F | Statement of Compressive Strength of Masonry | [7 empty] | X | [6 empty] | X
|  | 04 20 00 | 1.5 G | Field Quality control tests and inspection | [6 empty] | X | [8 empty] | X
|  | 04 20 00 | 1.5 H | Special Inspection Reports | [6 empty] | X | [8 empty] | X
|  | 04 20 00 | 1.5 I | Testing Agency and Special Inspectors | [7 empty] | X | [7 empty] | X
STRUCTURAL STEEL FRAMING
|  | 05 12 00 | 1.4 A | For each type |  |  | X | [12 empty] | X
|  | 05 12 00 | 1.4 B | LEED documentation for recycled content | [12 empty] | X |  | X
|  | 05 12 00 | 1.4 C | Detail fabrication of structural steel |  | X | [13 empty] | X
|  | 05 12 00 | 1.4 D | Welding certificates | [7 empty] | X | [7 empty] | X
|  | 05 12 00 | 1.4 E | Mill test reports, hardware, direct-tension indicators, shop primers, anchor and threaded rods, anchors, and grout | [6 empty] | X | [7 empty] | X
|  | 05 12 00 | 1.4 F | Manufacturer Certifications | [7 empty] | X | [6 empty] | X
|  | 05 12 00 | 1.4 G | Special inspection reports | [6 empty] | X | [8 empty] | X
|  | 05 12 00 | 1.4 H | Erector, Fabricator, Special Inspector qualifications | [7 empty] | X | [7 empty] | X
STEEL JOIST FRAMING
|  | 05 21 00 | 1.2 A | For each type of joist, accessory, and product indicated. |  |  | X | [12 empty] | X
|  | 05 21 00 | 1.2 B | LEED documentation for recycled content and/or VOC documentation |  |  | X | [9 empty] | X |  | X
|  | 05 21 00 | 1.2 C | Show layout, mark, number, type, location, and spacings of joists. Indicate locations and details of anchorage devices and bearing plates. Submit calculations sealed by a Professional Engineer. |  | X | [13 empty] | X
|  | 05 21 00 | 1.2 D | Field quality-control test reports | [6 empty] | X | [8 empty] | X
|  | 05 21 00 | 1.2 E | Welding certificates | [7 empty] | X | [6 empty] | X
|  | 05 21 00 | 1.2 F | Installer and special inspector qualifications | [7 empty] | X | [7 empty] | X
STEEL DECKING
|  | 05 30 00 | 1.2 A | For each type |  |  | X | [12 empty] | X
|  | 05 30 00 | 1.2 B | LEED documentation for recycled content and/or VOC documentation |  |  | X | [9 empty] | X |  | X
|  | 05 30 00 | 1.2 C | Show layout and types |  | X | [13 empty] | X
|  | 05 30 00 | 1.2 D | Field quality-control test and inspection reports. | [6 empty] | X | [8 empty] | X
|  | 05 30 00 | 1.2 E | Welding certificates | [7 empty] | X | [6 empty] | X
|  | 05 30 00 | 1.2 F | Installer and special inspector qualifications | [7 empty] | X | [7 empty] | X
COLD-FORMED METAL FRAMING
|  | 05 40 00 | 1.4 A | For each type |  |  | X | [11 empty] | X
|  | 05 40 00 | 1.4 B | LEED documentation for recycled content |  |  | X | [9 empty] | X |  | X
|  | 05 40 00 | 1.4 C | Welding Certificate | [7 empty] | X | [7 empty] | X
|  | 05 40 00 | 1.4 D | Special Inspection Reports | [9 empty] | X | [5 empty] | X
|  | 05 40 00 | 1.4 E | Include layout, spacing, sizes, thicknesses, and types of cold-formed steel framing; fabrication; and fastening and anchorage details, including mechanical fasteners. |  | X | [13 empty] | X
|  | 05 40 00 | 1.4 F | For framing and connections | [5 empty] | X | [9 empty] | X
|  | 05 40 00 | 1.4 G | Installer and special inspector qualifications | [7 empty] | X | [7 empty] | X
METAL FABRICATIONS
|  | 05 50 13 | 1.3 A | Include plans, elevations, sections, details |  | X | [13 empty] | X
|  | 05 50 13 | 1.3 B | Each type |  |  |  |  | X | [10 empty] | X
|  | 05 50 13 | 1.3 C | Welding certificates | [7 empty] | X | [6 empty] | X
|  | 05 50 13 | 1.3 D | Special inspection reports | [6 empty] | X | [8 empty] | X
|  | 05 50 13 | 1.3 E | For each type |  |  | X | [12 empty] | X
|  | 05 50 13 | 1.3 F | For each installed product | [5 empty] | X | [9 empty] | X
|  | 05 50 13 | 1.3 G | LEED documentation for recycled content |  |  | X | [9 empty] | X |  | X
|  | 05 50 13 | 1.3 H | Qualfication Data | [7 empty] | X | [7 empty] | X
METAL STAIRS
|  | 05 51 00 | 1.3 A | LEED documentation for recycled content |  |  | X | [9 empty] | X |  | X
|  | 05 51 00 | 1.3 B | Include plans, elevations, sections, details |  | X | [13 empty] | X
|  | 05 51 00 | 1.3 C | Welding certificates | [7 empty] | X | [6 empty] | X
|  | 05 51 00 | 1.3 D | Special inspection reports | [6 empty] | X | [8 empty] | X
|  | 05 51 00 | 1.3 E | For each installed product | [5 empty] | X | [9 empty] | X
PIPE RAILINGS
|  | 05 52 00 | 1.3 A | LEED documentation for recycled content |  |  | X | [9 empty] | X |  | X
|  | 05 52 00 | 1.3 B | Include plans, elevations, sections, details, and attachments to other work. |  | X | [14 empty] | X
|  | 05 52 00 | 1.3 C | Welding Certificates | [7 empty] | X | [8 empty] | X
|  | 05 52 00 | 1.3 D | Special Inspection Reports | [6 empty] | X | [9 empty] | X
|  | 05 52 00 | 1.3 E | For installed products indicated to comply with performance requirements and design criteria, including analysis data signed and sealed by the qualified professional engineer responsible for their preparation. Include design submittal with the corresponding shop drawings. | [5 empty] | X | [10 empty] | X
ROUGH CARPENTRY
|  | 06 10 00 | 1.3 A | For each type of process and product |  |  | X | [12 empty] | X
|  | 06 10 00 | 1.3 B | LEED documentation for chain of custody. VOC content, formaldehyde verification | [12 empty] | X |  | X
SHEATHING
|  | 06 16 00 | 1.2 A | For each type of process and product |  |  | X | [12 empty] | X
|  | 06 16 00 | 1.2 B | LEED documentation for chain of custody. VOC content, formaldehyde verification | [12 empty] | X |  | X
INTERIOR ARCHITECTURAL WOODWORK
|  | 06 40 23 | 1.3A | All products |  |  | X | [12 empty] | X
|  | 06 40 23 | 1.3B | LEED documentation for chain of custody. Recycled content, VOC content, formaldehyde verification | [12 empty] | X |  | X
|  | 06 40 23 | 1.3C | Show location of each cabinet, dimensioned plans and elevations, large-scale details, attachment devices, and other components. |  | X | [13 empty] | X
|  | 06 40 23 | 1.3D | All products and finishes |  |  |  |  | X | [10 empty] | X
FIBERGLASS REINFORCED PANELING
|  | 06 83 16 | 1.2 A | For each type of product |  |  | X | [12 empty] | X
|  | 06 83 16 | 1.2 B | For Adhesives and Sealants - VOC | [12 empty] | X |  | X
WATER REPELLENTS
|  | 07 19 00 | 1.3 A | For each type |  |  | X | [12 empty] | X
|  | 07 19 00 | 1.3 B | For each type | [6 empty] | X | [7 empty] | X
|  | 07 19 00 | 1.3 C | Color Selection |  |  |  |  | X | [10 empty] | X
|  | 07 19 00 | 1.3 D | Warranty |  |  |  | X | [11 empty] | X
|  | 07 19 00 | 1.3 E | Installer Qualifications | [7 empty] | X | [7 empty] | X
ACRYLIC WATER REPELLENT STAINS
|  | 07 19 13 | 1.2 A | For each type |  |  | X | [12 empty] | X
|  | 07 19 13 | 1.2 B | Verification Samples |  |  |  |  | X | [10 empty] | X
THERMAL INSULATION
|  | 07 21 00 | 1.2 A | For each type of insulation product |  |  | X | [12 empty] | X
|  | 07 21 00 | 1.2 B | LEED documentation for recycled content | [12 empty] | X |  | X
EXTERIOR INSULATION AND FINISH SYSTEMS (EIFS)
|  | 07 24 00 | 1.4 A | For all products |  |  | X | [12 empty] | X
|  | 07 24 00 | 1.4 B | LEED documentation for recycled content, VOC content for adhesives and sealants |  |  | X | [9 empty] | X |  | X
|  | 07 24 00 | 1.4 C | 24" square panel for each type product. Include sealant samples to verify color selected. |  |  |  |  | X | [10 empty] | X
|  | 07 24 00 | 1.4 D | Certifying that EIFS and joint sealants comply with requirements. | [7 empty] | X | [6 empty] | X
|  | 07 24 00 | 1.4 E | Compatibility and adhesion test reports. | [6 empty] | X | [7 empty] | X
|  | 07 24 00 | 1.4 F | Evaluation reports: For water-resistive coating, code compliance, and EIFS systems (including insulation), from ICC Evaluation Services, LLC. | [6 empty] | X | [7 empty] | X
|  | 07 24 00 | 1.4 G | Field quality-control special inspection reports. | [9 empty] | X |  |  |  |  | X
METAL PANELS
|  | 07 40 00 | 1.3 A | All products |  |  | X | [12 empty] | X
|  | 07 40 00 | 1.3 B | Include plans, elevations, sections, details, and attachments to other work. 2. Include details of edge conditions, joints, panel profiles, corners, anchorages, trim, flashings, closures, and accessories. |  | X | [13 empty] | X
|  | 07 40 00 | 1.3 C | Warranties |  |  |  | X | [10 empty] | X
|  | 07 40 00 | 1.3 D | LEED documentation for recycled content, VOC content for adhesives and sealants |  |  | X | [9 empty] | X |  | X
|  | 07 40 00 | 1.3 E | Each exposed finish |  |  |  |  | X | [10 empty] | X
MODIFIED BITUMINOUS MEMBRANE ROOFING
|  | 07 52 00 | 1.4 A | Product Data for roofing system |  |  | X | [12 empty] | X
|  | 07 52 00 | 1.4 B | VOC content for adhesives and sealants |  |  | X | [9 empty] | X |  | X
|  | 07 52 00 | 1.4 C | Shop Drawings |  | X | [13 empty] | X
|  | 07 52 00 | 1.4 D | Installer Certificates | [7 empty] | X | [6 empty] | X
|  | 07 52 00 | 1.4 E | Manufacturer Certificates | [7 empty] | X | [6 empty] | X
|  | 07 52 00 | 1.4 F | Product Test Reports | [6 empty] | X | [7 empty] | X
|  | 07 52 00 | 1.4 G | Maintenance Data | [11 empty] | X |  |  | X
|  | 07 52 00 | 1.4 H | Warranties |  |  |  | X | [12 empty] | X
|  | 07 52 00 | 1.4 I | Inspection Report | [6 empty] | X | [7 empty] | X
ROOFING SYSTEM MODIFICATIONS
|  | 07 52 05 | 1.3 B | Warranty |  |  |  |  | X | [11 empty] | X
|  | 07 52 05 | 1.4 A | Installer Qualifications | X | [15 empty] | X
ETHYLENE-PROPYLENE-DIENE-MONOMER ROOFING (BLACK)
|  | 07 53 23 | 1.4 A | For all products |  |  | X | [12 empty] | X
|  | 07 53 23 | 1.4 B | VOC content for adhesives and sealants |  |  | X | [9 empty] | X |  | X
|  | 07 53 23 | 1.4 C | Roofing system |  | X | [13 empty] | X
|  | 07 53 23 | 1.4 D | Installer Certificates | [7 empty] | X | [6 empty] | X
|  | 07 53 23 | 1.4 E | Manufacturer Certificates | [7 empty] | X | [6 empty] | X
|  | 07 53 23 | 1.4 F | Product Test Reports | [6 empty] | X | [7 empty] | X
|  | 07 53 23 | 1.4 G | For roofing system including maintenance manuals | [11 empty] | X |  |  | X
|  | 07 53 23 | 1.4 H | Warranties |  |  |  | X | [10 empty] | X
|  | 07 53 23 | 1.4 I | Inspection Report | [6 empty] | X | [7 empty] | X
ETHYLENE-PROPYLENE-DIENE-MONOMER ROOFING (WHITE)
|  | 07 53 23 | 1.4 A | For all products |  |  | X | [12 empty] | X
|  | 07 53 23 | 1.4 B | LEED documentation for solar reflectance, VOC content for adhesives and sealants |  |  | X | [9 empty] | X |  | X
|  | 07 53 23 | 1.4 C | Roofing system |  | X | [13 empty] | X
|  | 07 53 23 | 1.4 D | Installer Certificates | [7 empty] | X | [6 empty] | X
|  | 07 53 23 | 1.4 E | Manufacturer Certificates | [7 empty] | X | [6 empty] | X
|  | 07 53 23 | 1.4 F | Product Test Reports | [6 empty] | X | [7 empty] | X
|  | 07 53 23 | 1.4 G | For roofing system including maintenance manuals | [11 empty] | X |  |  | X
|  | 07 53 23 | 1.4 H | Warranties |  |  |  | X | [10 empty] | X
|  | 07 53 23 | 1.4 I | Inspection Report | [6 empty] | X | [7 empty] | X
SHEET METAL FLASHING AND TRIM
|  | 07 60 00 | 1.3A | Layout, joining, profiles, and anchorages, plans and elevations of all fabricated work |  | X | [13 empty] | X
|  | 07 60 00 | 1.3B | LEED documentation for recycled content | [12 empty] | X |  | X
|  | 07 60 00 | 1.3C | For each type of exposed finish required |  |  |  |  | X | [10 empty] | X
ROOF SPECIALTIES
|  | 07 71 00 | 1.3 A | Each type of product. |  |  | X | [12 empty] | X
|  | 07 71 00 | 1.3 B | For roof specialties. Include plans, elevations, expansion-joint locations, keyed details, and attachments to other work. Distinguish between plant- and field-assembled work. |  | X | [13 empty] | X
|  | 07 71 00 | 1.3 C | For copings and roof-edge flashings made from 12-inch lengths of full-size components including fasteners, cover joints, accessories, and attachments. |  |  |  |  | X | [10 empty] | X
|  | 07 71 00 | 1.3 D | Based on evaluation of comprehensive tests performed by a qualified testing agency, for copings and roof-edge flashings indicating performance requirements. | [6 empty] | X | [7 empty] | X
|  | 07 71 00 | 1.3 E | Warranties |  |  |  | X | [10 empty] | X
ROOF HATCHES
|  | 07 72 33 | 1.3 A | Each type of product. |  |  | X | [12 empty] | X
FIRESTOPPING
|  | 07 84 00 | 1.3A | For each product |  |  | X | [11 empty] | X
|  | 07 84 00 | 1.3B | VOC content for adhesives and sealants |  |  | X | [9 empty] | X |  | X
|  | 07 84 00 | 1.3C | For each firestop system |  | X | [12 empty] | X
|  | 07 84 00 | 1.3D | Field quality test reports | [6 empty] | X | [7 empty] | X
JOINT SEALANTS
|  | 07 92 00 | 1.3A | For each joint-sealant product indicated. |  |  | X | [12 empty] | X
|  | 07 92 00 | 1.3B | VOC content for adhesives and sealants |  |  | X | [9 empty] | X |  | X
|  | 07 92 00 | 1.3C | For each kind and color of joint sealant required |  |  |  |  | X | [10 empty] | X
|  | 07 92 00 | 1.3D | Preconstruction Compatibility and Adhesion Test Reports | X | [5 empty] | X | X | [6 empty] | X
|  | 07 92 00 | 1.3E | Product test reports | [6 empty] | X | [7 empty] | X
|  | 07 92 00 | 1.3F | Preconstruction Field-Adhesion Test Reports | X | [6 empty] | X | [6 empty] | X
|  | 07 92 00 | 1.3G | Sealant, Waterproofing, and Restoration Institute (SWRI) Validation Certificate | [7 empty] | X | [6 empty] | X
COMMISSIONING OF OPENINGS
|  | 08 08 00 |  | Commissioning submittals | [15 empty] | X
HOLLOW METAL DOORS AND FRAMES
|  | 08 11 13 | 1.4A | Manufacturer's product description, installation and maintenance instructions for each type and size of traffic door |  |  | X | [8 empty] | X |  |  |  | X
|  | 08 11 13 | 1.4B | Schedules, details, elevations of doors and frames |  | X | [13 empty] | X
|  | 08 11 13 | 1.4C | LEED documentation for recycled content, VOC content for adhesives and sealants |  |  | X | [9 empty] | X |  |  | X
|  | 08 11 13 | 1.4D | Drawings of each opening, including door and frame, drawn to scale and coordinating door hardware |  | X | [13 empty] | X
FLUSH WOOD DOORS
|  | 08 14 16 | 1.2A | For each type door, core, edge, trim, finish |  |  | X | [12 empty] | X
|  | 08 14 16 | 1.2B | LEED documentation for chain of custody, VOC content for adhesives and sealants | [12 empty] | X |  | X
|  | 08 14 16 | 1.2C | Indicate location, size, and hand of each door, elevation of each kind of door, details, hardware blocking |  | X | [13 empty] | X
|  | 08 14 16 | 1.2D | Factory finishes, face materials, wood species, transparent finishes, corner sections, and edgings |  |  |  |  | X | [10 empty] | X
ACCESS DOORS AND FRAMES
|  | 08 31 13 | 1.2A | For each type of access door assembly specified, including details of construction relative to materials, individual components, profiles, and finishes. |  |  | X | [12 empty] | X
|  | 08 31 13 | 1.2B | LEED documentation for recycled content, VOC content for adhesives and sealants |  |  | X | [9 empty] | X |  |  | X
OVERHEAD COILING DOORS
|  | 08 33 23 | 1.4A | For each type product |  |  | X | [12 empty] | X
|  | 08 33 23 | 1.4B | LEED documentation for recycled content, VOC content for adhesives and sealants |  |  | X | [9 empty] | X |  |  | X
|  | 08 33 23 | 1.4C | Delegated Design Submittal | [5 empty] | X | [8 empty] | X
SECTIONAL DOORS
|  | 08 36 13 | 1.4A | For each type product |  |  | X | [12 empty] | X
|  | 08 36 13 | 1.4B | LEED documentation for recycled content, VOC content for adhesives and sealants |  |  | X | [9 empty] | X |  | X
|  | 08 36 13 | 1.4C | Delegated Design Submittal | [5 empty] | X | [8 empty] | X
TRAFFIC DOORS
|  | 08 38 00 | 1.2A | For each type product |  |  | X | [12 empty] | X
|  | 08 38 00 | 1.2B | LEED documentation for recycled content, VOC content for adhesives and sealants |  |  | X | [9 empty] | X |  | X
ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS
|  | 08 41 13 | 1.3A | For each type product |  |  | X | [12 empty] | X
|  | 08 41 13 | 1.3B | LEED documentation for recycled content, VOC content for adhesives and sealants |  |  | X | [9 empty] | X |  | X
|  | 08 41 13 | 1.3C | Include plans, elevations, sections, details |  | X | [13 empty] | X
|  | 08 41 13 | 1.3D | Product Test Reports | [6 empty] | X | [7 empty] | X
|  | 08 41 13 | 1.3E | Seismic Qualification Certificates | [7 empty] | X | [6 empty] | X
SLIDING AUTOMATIC ENTRANCES
|  | 08 42 29.23 | 1.4A | For each type product |  |  | X | [12 empty] | X
|  | 08 42 29.23 | 1.4B | Include plans, elevations, sections, details |  | X | [13 empty] | X
|  | 08 42 29.23 | 1.4C | VOC content for adhesives and sealants | [12 empty] | X |  | X
|  | 08 42 29.23 | 1.4D | For each type of exposed finish required |  |  |  |  | X | [10 empty] | X
|  | 08 42 29.23 | 1.4E | Product Test Reports | [6 empty] | X | [8 empty] | X
|  | 08 42 29.23 | 1.4F | For door operators and control systems | [11 empty] | X |  |  | X
BLAST RESISTANT SLIDING AUTOMATIC ENTRANCES WITH BREAK-AWAY
|  | 08 42 29.63 | 1.5A | For each type product |  |  | X | [12 empty] | X
|  | 08 42 29.63 | 1.5B | Include plans, elevations, sections, details |  | X | [13 empty] | X
|  | 08 42 29.63 | 1.5C | VOC content for adhesives and sealants |  |  | X | [9 empty] | X |  | X
|  | 08 42 29.63 | 1.5D | For each type of exposed finish required |  |  |  |  | X | [10 empty] | X
|  | 08 42 29.63 | 1.5E | Product Test Reports | [6 empty] | X | [8 empty] | X
|  | 08 42 29.63 | 1.5F | Manufacturers field reports | [10 empty] | X |  |  |  | X
|  | 08 42 29.63 | 1.5G | For door operators and control systems | [11 empty] | X |  |  | X
|  | 08 42 29.63 | 1.5H | Warranties |  |  |  | X | [10 empty] | X
DAYLIGHTING
|  | 08 62 00 | 1.4A | For each type product |  |  | X | [12 empty] | X
|  | 08 62 00 | 1.4B | Include plans, elevations, sections, details |  | X | [13 empty] | X
|  | 08 62 00 | 1.4C | LEED documentation for recycled content, regional materials, VOC content for adhesives and sealants | [12 empty] | X |  | X
|  | 08 62 00 | 1.4D | Product Test Reports | [6 empty] | X | [7 empty] | X
DOOR HARDWARE
|  | 08 71 00 | 1.2A | For each type of product |  |  | X | [5 empty] | X |  |  | X |  |  |  |  | X
|  | 08 71 00 | 1.2B | Certify that locksets approved for use complies with “Buy American Act". | [7 empty] | X | [6 empty] | X
|  | 08 71 00 | 1.2C | LEED documentation for recycled content, VOC content for adhesives and sealants | [12 empty] | X |  | X
|  | 08 71 00 | 1.2D | Hardware Sets |  | X | [14 empty] | X
|  | 08 71 00 | 1.2E | Keying Schedule | [8 empty] | X | [7 empty] | X
|  | 08 71 00 | 1.2F | AHC Report | [6 empty] | X | X | [6 empty] | X
|  | 08 71 00 | 1.2G | Product test report | [6 empty] | X | [7 empty] | X
KEY STORAGE EQUIPMENT
|  | 08 79 13 | 1.2A | For each type product |  |  | X | [12 empty] | X
|  | 08 79 13 | 1.2B | Key control system instruction program | [11 empty] | X |  |  |  | X
GLAZING
|  | 08 81 00 | 1.5A | For each type product |  |  | X | [12 empty] | X
|  | 08 81 00 | 1.5B | VOC content for adhesives and sealants | [12 empty] | X |  | X
|  | 08 81 00 | 1.5C | Glazing Schedule |  | X | [13 empty] | X
|  | 08 81 00 | 1.5D | Product certificates | [7 empty] | X | [7 empty] | X
|  | 08 81 00 | 1.5E | Preconstruction adhesion and test reports | [6 empty] | X | [7 empty] | X
|  | 08 81 00 | 1.5F | Field quality control reports | [9 empty] | X | [5 empty] | X
MIRRORS
|  | 08 83 00 | 1.2A | Preconstruction Test Reports | [6 empty] | X | [7 empty] | X
|  | 08 83 00 | 1.2B | VOC content for adhesives and sealants | [12 empty] | X |  | X
|  | 08 83 00 | 1.2C | Sample of special warranty |  |  |  | X | [10 empty] | X
COMMON WORK RESULTS FOR FLOORING PREPARATION
|  | 09 05 61 | 1.4 A | For each type product |  |  | X | [12 empty] | X
|  | 09 05 61 | 1.4 B | Moisture and pH; floor plans and photos | [6 empty] | X | [8 empty] | X
|  | 09 05 61 | 1.4 C | Bond and Compatibility Test report | [6 empty] | X | [8 empty] | X
|  | 09 05 61 | 1.4 D | Remedial materials product data |  |  | X | [11 empty] | X
PORTLAND CEMENT PLASTER
|  | 09 24 23 | 1.2A | For each type product |  |  | X | [12 empty] | X
|  | 09 24 23 | 1.2B | LEED documentation for recycled content, VOC content for adhesives and sealants | [12 empty] | X |  | X
|  | 09 24 23 | 1.2C | Locations and installation of control and expansion joints |  | X | [13 empty] | X
|  | 09 24 23 | 1.2D | For each type of finish coat |  |  |  |  | X | [10 empty] | X
GYPSUM BOARD
|  | 09 29 00 | 1.2A | For each type product |  |  | X | [12 empty] | X
|  | 09 29 00 | 1.2B | LEED documentation for recycled content, regional materials, VOC content for adhesives and sealants | [12 empty] | X |  | X
|  | 09 29 00 | 1.2C | Plans, elevations, sections and details of components, and attachments to other units |  | X | [13 empty] | X
|  | 09 29 00 | 1.2D | Steel framing | [5 empty] | X | [9 empty] | X
TILING
|  | 09 30 00 | 1.3A | For each type product |  |  | X | [12 empty] | X
|  | 09 30 00 | 1.3B | LEED documentation for recycled content, VOC content for adhesives and sealants | [12 empty] | X |  | X
|  | 09 30 00 | 1.3C | Assembled samples with grouted joints for each type tile and each color and finish |  |  |  |  | X | [10 empty] | X
ACOUSTICAL CEILINGS
|  | 09 51 00 | 1.3A | Each type of acoustical ceiling unit and suspension system |  |  | X | [12 empty] | X
|  | 09 51 00 | 1.3B | LEED documentation for recycled content, VOC content for adhesives and sealants | [12 empty] | X |  | X
|  | 09 51 00 | 1.3C | Delegated design submittal | [5 empty] | X | [9 empty] | X
|  | 09 51 00 | 1.3D | Field quality reports | [9 empty] | X |  |  |  |  | X
|  | 09 51 00 | 1.3E | Qualification for testing agency | [7 empty] | X | [6 empty] | X
|  | 09 51 00 | 1.3F | For each acoustical panel ceiling | [6 empty] | X | [7 empty] | X
|  | 09 51 00 | 1.3G | For each acoustical panel ceiling | [6 empty] | X | [7 empty] | X
|  | 09 51 00 | 1.3H | For finishes to include in maintenance manuals | [11 empty] | X |  |  | X
RESILIENT TILE FLOORING
|  | 09 65 19 | 1.2A | Each type of product |  |  | X | [12 empty] | X
|  | 09 65 19 | 1.2B | LEED documentation for recycled content, VOC content for adhesives and sealants | [12 empty] | X |  | X
|  | 09 65 19 | 1.2C | Full-size units of each color and pattern of resilient floor tile |  |  |  |  | X | [10 empty] | X
|  | 09 65 19 | 1.2D | Each type of product | [11 empty] | X |  |  | X
|  | 09 65 19 | 1.2E | Moisture/Bond Tests | [6 empty] | X | [7 empty] | X
RESINOUS FLOORING
|  | 09 67 23 | 1.3A | Each type of product |  |  | X | [12 empty] | X
|  | 09 67 23 | 1.3B | VOC content for adhesives and sealants | [12 empty] | X |  | X
|  | 09 67 23 | 1.3C | For each resinous flooring system |  | X | [13 empty] | X
PAINTING AND COATING
|  | 09 90 00 | 1.2A | Each type of product |  |  | X | [12 empty] | X
|  | 09 90 00 | 1.2B | VOC content for adhesives and sealants | [12 empty] | X |  | X
|  | 09 90 00 | 1.2C | Each color, texture, and pattern required |  |  |  |  | X | [10 empty] | X
|  | 09 90 00 | 1.2D | MPI Approved Products List | [6 empty] | X | [7 empty] | X
VISUAL DISPLAY SURFACES
|  | 10 10 00 | 1.2A | For each type product |  |  | X | [12 empty] | X
|  | 10 10 00 | 1.2B | VOC content for adhesives and sealants | [12 empty] | X |  | X
|  | 10 10 00 | 1.2C | For each type of visual display surface |  |  |  |  | X | [10 empty] | X
SIGNAGE
|  | 10 14 00 | 1.3A | For each type product |  |  | X | [12 empty] | X
|  | 10 14 00 | 1.3B | VOC content for adhesives and sealants | [12 empty] | X |  |  | X
|  | 10 14 00 | 1.3C | Showing fabrication and erection of signs |  | X | [13 empty] | X
|  | 10 14 00 | 1.3D | Sign message verification |  | X | [14 empty] | X
INTERIOR DÉCOR SPECIALTIES
|  | 10 15 00 | 1.3A | For each type of interior décor |  |  | X | [12 empty] | X
|  | 10 15 00 | 1.3B | Show fabrication and erection of interior décor specialties. Include plans, elevations, and large-scale sections |  | X | [13 empty] | X
|  | 10 15 00 | 1.3C | For each type of interior décor |  |  |  |  | X | [10 empty] | X
|  | 10 15 00 | 1.3D | LEED documentation for chain of custody. VOC content, formaldehyde verification | [12 empty] | X |  | X
TOILET COMPARTMENTS
|  | 10 21 13 | 1.2A | For each type product |  |  | X | [12 empty] | X
|  | 10 21 13 | 1.2B | LEED documentation for recycled content | [12 empty] | X |  | X
|  | 10 21 13 | 1.2C | Include plans, elevations, sections, details, and attachments to other work |  | X | [13 empty] | X
WIRE MESH PARTITIONS
|  | 10 22 13 | 1.4A | For each type product |  |  | X | [12 empty] | X
|  | 10 22 13 | 1.4B | Include plans, elevations, sections, details, and attachments to other work |  | X | [13 empty] | X
|  | 10 22 13 | 1.4C | Maintenance data | [11 empty] | X |  |  | X
WALL AND EQUIPMENT PROTECTION
|  | 10 26 00 | 1.2A | Include construction details, material descriptions, impact strength, dimensions of individual components and profiles, and finishes for each type of product indicated |  |  | X | [12 empty] | X
|  | 10 26 00 | 1.2B | LEED documentation for recycled content, VOC content for adhesives and sealants | [12 empty] | X |  | X
TOILET ACCESSORIES
|  | 10 28 13 | 1.2A | For each type product |  |  | X | [12 empty] | X
|  | 10 28 13 | 1.2B | Indicating types, quantities, sizes, and installation locations by room of each accessory required | [5 empty] | X | [9 empty] | X
FIRE PROTECTION SPECIALTIES
|  | 10 44 00 | 1.2A | For fire extinguishers and cabinets |  |  | X | [12 empty] | X
METAL LOCKERS
|  | 10 51 13 | 1.3A | For each type product |  |  | X | [12 empty] | X
ROTATING MODULAR SYSTEM
|  | 10 56 23 | 1.3A | For each item of equipment required |  |  | X | [12 empty] | X
STORAGE RACKS
|  | 10 56 29 | 1.3A | For each type product |  |  | X | [12 empty] | X
COMMISSIONING OF EQUIPMENT
|  | 11 08 00 |  | Commissioning submittals | [13 empty] | X |  | X
LOADING DOCK EQUIPMENT
|  | 11 13 00 | 1.3 | For each item of product |  | X | X | X | X | [10 empty] | X
|  | 11 13 00 | 1.3 | For each item of product | [7 empty] | X |  |  |  | X |  |  | X
SAFES
|  | 11 16 00 | 1.2 | Include standard details and maintenance |  |  | X | [8 empty] | X |  |  |  | X
TELLER AND SERVICE EQUIPMENT
|  | 11 17 00 | 1.2 | Include standard details and maintenance |  |  | X | [8 empty] | X |  |  |  | X
BAKERY EQUIPMENT
|  | 11 40 00.13 | 1.2A | For each item of equipment |  |  | X | [12 empty] | X
DELI EQUIPMENT
|  | 11 40 00.16 | 1.2A | For each item of equipment |  |  | X | [12 empty] | X
MEAT DEPARTMENT EQUIPMENT
|  | 11 40 00.23 | 1.2A | For each item of equipment |  |  | X | [12 empty] | X
PRODUCE DEPARTMENT EQUIPMENT
|  | 11 40 00.26 | 1.2A | For each item of equipment |  |  | X | [12 empty] | X
SEAFOOD DEPARTMENT EQUIPMENT
|  | 11 40 00.29 | 1.2A | For each item of equipment |  |  | X | [12 empty] | X
FACILITY WASTE BALERS
|  | 11 82 36 | 1.2A | For each item of equipment |  |  | X | [12 empty] | X
|  | 11 82 36 | 1.2B | Warranty |  |  |  | X | [11 empty] | X
HORIZONTAL LOUVER BLINDS
|  | 12 21 13 | 1.2A | For each type product |  |  | X | [12 empty] | X
|  | 12 21 13 | 1.2B | Samples for verification |  |  |  |  | X | [10 empty] | X
|  | 12 21 13 | 1.2C | Window Treatment Schedule |  | X | [13 empty] | X
ENTRANCE CARPET TILE
|  | 12 48 13 | 1.2A | For each type product |  |  | X | [12 empty] | X
|  | 12 48 13 | 1.2B | Samples for verification |  |  |  |  | X | [10 empty] | X
|  | 12 48 13 | 1.2C | For each carpet tile | [11 empty] | X |  |  | X
|  | 12 48 13 | 1.2D | Moisture/Bond Tests | [6 empty] | X | [7 empty] | X
SYSTEMS FURNITURE
|  | 12 59 00 | 1.2A | For each type product |  |  | X | [12 empty] | X
SITE FURNISHINGS
|  | 12 93 00 | 1.2A | For each type product |  |  | X | [12 empty] | X
|  | 12 93 00 | 1.2B | LEED documentation for recycled content | [12 empty] | X |  | X
COLD STORAGE ROOMS
|  | 13 21 26 | 1.3A | For each type unit |  |  | X | [12 empty] | X
|  | 13 21 26 | 1.3B | For each type unit |  | X | [13 empty] | X
|  | 13 21 26 | 1.3C | Show details of anchorage and connection, location and method of attachment and complette layout of panels |  | X | [12 empty] | X
|  | 13 21 26 | 1.3D | For each type unit | [8 empty] | X | [5 empty] | X
|  | 13 21 26 | 1.3E | Indicate location and loads imposed | [5 empty] | X | [8 empty] | X
|  | 13 21 26 | 1.3F | Operating and performance tests | [6 empty] | X | [8 empty] | X
|  | 13 21 26 | 1.3G | Manufacturers warranties |  |  |  | X | [10 empty] | X
COMMISSIONING OF FIRE SUPPRESSION
|  | 21 08 00 |  | Commissioning submittals | [13 empty] | X |  | X
FIRE-SUPPRESSION SPRINKLER SYSTEMS
|  | 21 13 00 | 1.4A | For each type product listed |  |  | X |  |  |  | X | [8 empty] | X
|  | 21 13 00 | 1.4A | Working plans and hydraulic calculations sealed with PE stamp; flow tests |  | X | [13 empty] | X
|  | 21 13 00 | 1.4A | For each type product listed |  |  |  |  | X | [10 empty] | X
|  | 21 13 00 | 1.4A | Operation and maintenance data | [11 empty] | X |  |  | X
|  | 21 13 00 | 1.4B | Project Record Docs; Manufacturer's certificate; operation and maintenance data; warranty; NFPA 25; certification and testing data | [13 empty] | X |  |  | X
|  | 21 13 00 | 1.4C | VOC content for adhesives and sealants | [12 empty] | X |  | X
FIRE PUMPS
|  | 21 30 00 | 1.5A | For each type product listed |  |  | X |  |  |  | X | [8 empty] | X
|  | 21 30 00 | 1.5A | Working plans and hydraulic calculations sealed with PE stamp; flow tests |  | X | [13 empty] | X
|  | 21 30 00 | 1.5A | Operation and maintenance data | [11 empty] | X |  |  | X
|  | 21 30 00 | 1.5B | Field Test Reports | [6 empty] | X | [7 empty] | X
|  | 21 30 00 | 1.5B | Manfuacturer's instructions | [8 empty] | X | [5 empty] | X
|  | 21 30 00 | 1.5c | Project Record Docs; Manufacturer's certificate; operation and maintenance data; warranty; NFPA 25; certification and testing data | [13 empty] | X |  |  | X
PLUMBING SPECIALTIES
|  | 22 05 19 | 1.3A | For all products |  |  | X | [8 empty] | X |  |  |  | X
|  | 22 05 19 | 1.3A | Indicate dimensions, weights, and placements of openings |  | X | [13 empty] | X
|  | 22 05 19 | 1.3A | Operation and Maintenance Data | [11 empty] | X |  |  |  | X
|  | 22 05 19 | 1.3B | Certify that grease interceptors meet or exceed specified requirements. | [7 empty] | X | [7 empty] | X
|  | 22 05 19 | 1.3B | Installation instructions, including assembly and support requirements | [8 empty] | X | [5 empty] | X
|  | 22 05 19 | 1.3C | Record actual locations of equipment, cleanouts, backflow preventers, water hammer arrestors, insrumentation | [10 empty] | X |  |  | X |  |  | X
|  | 22 05 19 | 1.3C | Indicate frequency of treatment required | [11 empty] | X |  | X |  |  | X
|  | 22 05 19 | 1.3C | Include instructions for calibrating instruments | [11 empty] | X |  | X |  |  | X
|  | 22 05 19 | 1.3C | Certification data that supplements previously submitted O & M Manuals | [11 empty] | X |  | X |  |  | X
VIBRATION AND SEISMIC CONTROLS FOR PLUMBING PIPING AND EQUIPMENT
|  | 22 05 48 | 1.5B | Indicate isolators, dynamic loads, restraints and loads |  | X | [13 empty] | X
|  | 22 05 48 | 1.5C | Provide product data for each isolator and restraint, and schedule of isolators and restraints. |  |  | X | [8 empty] | X |  |  |  | X
|  | 22 05 48 | 1.5D | Manufacturer's installation instructions | [8 empty] | X | [6 empty] | X
|  | 22 05 48 | 1.5E | Provide certification selection and design of isolators and restraints by engineer. | [5 empty] | X | [5 empty] | X |  |  |  | X
|  | 22 05 48 | 1.5F | Details of attachment to walls, floors, slabs, supplementary steel work | [5 empty] | X | [5 empty] | X |  |  |  | X
|  | 22 05 48 | 1.5G | Seismic restraint calculations | [5 empty] | X | [9 empty] | X
|  | 22 05 48 | 1.5H | Welding certificates | [7 empty] | X | [5 empty] | X |  | X
PLUMBING PIPING INSULATION
|  | 22 07 19 | 1.4A | Provide product data for each type of mechanical insulation identifying k-value, thickness, jackets (factory and field applied) and accessories. Include maintenance data. |  |  | X | [8 empty] | X |  |  |  | X
|  | 22 07 19 | 1.4B | VOC content for adhesives and sealants |  |  | X | [9 empty] | X |  | X
COMMISSIONING OF PLUMBING
|  | 22 08 00 |  | Commissioning submittals | [13 empty] | X |  | X
PLUMBING PIPING
|  | 22 10 00 | 1.4A | Provide data on pipe materials, pipe fittings, valves and accessories. |  |  | X | [12 empty] | X
|  | 22 10 00 | 1.4A | Provide manufacturers catalog; indicate valve data and ratings. | [11 empty] | X |  |  |  | X
|  | 22 10 00 | 1.4B | Record actual locations of valves | [10 empty] | X |  |  | X |  | X
|  | 22 10 00 | 1.4B | Certifications and testing supplemental to previously submitted O & M manuals. | [6 empty] | X | X | [5 empty] | X |  | X
PLUMBING EQUIPMENT
|  | 22 30 00 | 1.3A | Dimension drawings for water heaters, components, and connections |  |  | X | [8 empty] | X |  | X |  | X
|  | 22 30 00 | 1.3A | Pump type, capacity, power requirements, performance curves, operating points |  |  | X | [8 empty] | X |  | X |  | X
|  | 22 30 00 | 1.3A | Heat exchanger size dimensions, performance data |  | X | [9 empty] | X |  | X |  | X
|  | 22 30 00 | 1.3B | Manufacturer's instructions | [8 empty] | X |  |  | X |  | X | X
|  | 22 30 00 | 1.3C | Include operation, maintenance, and inspection data, replacement part numbers and availability, and service depot location and telephone number. | [11 empty] | X |  | X |  | X
|  | 22 30 00 | 1.3C | Water heater warranty |  |  |  | X | [9 empty] | X |  | X
|  | 22 30 00 | 1.3C | Certifications and testing data as a supplement to previously submitted O & M | [6 empty] | X | X | [5 empty] | X |  | X
PLUMBING FIXTURES
|  | 22 40 00 | 1.3A | Provide catalog illustrations of fixtures, electric/electronic controls for lavatories and flush valves, sizes, rough-in dimensions, utility sizes, trim, and finishes. |  |  | X | [8 empty] | X |  |  |  |  | X
|  | 22 40 00 | 1.3B | Indicate installation methods and procedures. | [8 empty] | X | [5 empty] | X
|  | 22 40 00 | 1.3C | Maintenance Data: Include fixture trim exploded view and replacement parts lists. | [11 empty] | X |  | X |  |  | X
|  | 22 40 00 | 1.3C | Warranties |  |  |  | X | [9 empty] | X |  |  | X
|  | 22 40 00 | 1.3C | Submit all certifications and testing data as a supplement to previously submitted O & M manuals at contract closeout. | [6 empty] | X | X | [5 empty] | X |  |  | X
COMMON WORK RESULTS FOR HVAC
|  | 23 05 00 | 1.6B | Prior to approval of the material to be used, the manufacturer shall furnish written certification that the material contains no asbestos. | [7 empty] | X | [8 empty] | X
COMMON MOTOR REQUIREMENTS FOR HVAC EQUIPMENT
|  | 23 05 13 | 1.3A | For each type and size of motor, provide nameplate data and ratings; shipping, installed, and operating weights; mounting arrangements; size, type, and location of winding terminations; conduit entry and ground lug locations; and information on coatings or finishes |  |  | X | [12 empty] | X
|  | 23 05 13 | 1.3B | Dimensioned Plans, Elevations, Sections, and Details, including required clearances and service space around equipment |  | X | [13 empty] | X
|  | 23 05 13 | 1.3C | Field Quality test reports | [6 empty] | X | [8 empty] | X
|  | 23 05 13 | 1.3D | For field-installed motors to be included in operation and maintenance manuals | [11 empty] | X |  |  | X
EXPANSION FITTINGS AND LOOPS FOR HVAC PIPING
|  | 23 05 16 | 1.3B | Indicate maximum temperature and pressure rating, face-to-face length, live length, hose wall thickness, hose convolutions per foot and per assembly, fundamental frequency of assembly, braid structure, and total number of wires in braid; dimensions and ratings; design data and calculations |  |  | X |  |  | X | [9 empty] | X
|  | 23 05 16 | 1.3C | Indicate special procedures, and external controls | [8 empty] | X | [6 empty] | X
|  | 23 05 16 | 1.3D | Operation and Maintenance Data | [11 empty] | X |  |  | X
METERS AND GAGES FOR HVAC PIPING
|  | 23 05 19 | 1.3A | Provide manufacturers data and list which indicates use, operating range, total range, accuracy, and location for manufactured components; operation and maintenance data |  |  | X |  |  | X | [5 empty] | X |  |  |  | X
|  | 23 05 19 | 1.3B | Record actual locations of components and instrumentation; include instructions for calibrating instruments. | [10 empty] | X | X |  | X
VIBRATION AND SEISMIC CONTROLS FOR HVAC AND PIPING AND EQUIPMENT
|  | 23 05 48 | 1.5B | Indicate and locate vibration isolators, with static and dynamic load on each |  | X | [14 empty] | X
|  | 23 05 48 | 1.5C | For each type |  |  | X | [13 empty] | X
|  | 23 05 48 | 1.5D | Manufacturer's installation instructions | [8 empty] | X | [7 empty] | X
|  | 23 05 48 | 1.5E | Certify that seismic restraints have been selected and designed by a licensed professional engineer, licensed to practice in the state where the restraints are being installed, to meet or exceed specified requirements | [7 empty] | X | [8 empty] | X
|  | 23 05 48 | 1.5F | Include spacing, static loads and seismic loads at all attachment and support points | [5 empty] | X | [10 empty] | X
|  | 23 05 48 | 1.5G | Seismic restraint calculations must be provided for all connections of equipment to the structure and stamped by professional PE | [5 empty] | X | [10 empty] | X
|  | 23 05 48 | 1.5H | Welding certificates | [7 empty] | X | [8 empty] | X
TESTING, ADJUSTING, AND BALANCING FOR HVAC
|  | 23 05 93 | 1.4B | Air Balance Report | [6 empty] | X | [5 empty] | X |  |  |  | X
|  | 23 05 93 | 1.4C | Submit name of adjusting and balancing agency for approval within 30 days after award of Contract. | X | [15 empty] | X
|  | 23 05 93 | 1.4D | Within 60 days of General Contract award conduct and review a TAB design review detailing and items that would prevent the successful balancing of the systems. | X | [15 empty] | X
|  | 23 05 93 | 1.4E | Field Reports: Indicate deficiencies in systems that would prevent proper testing, adjusting, and balancing of systems and equipment to achieve specified performance. | X | [15 empty] | X
|  | 23 05 93 | 1.4F | Prior to commencing work, submit report forms or outlines indicating adjusting, balancing, and equipment data required. | X | [15 empty] | X
|  | 23 05 93 | 1.4G | Submit draft copies of report for review prior to final acceptance of Project. Provide final copies for Architect/Engineer and for inclusion in operating and maintenance manuals. | [6 empty] | X | [9 empty] | X
|  | 23 05 93 | 1.4F | For all products and systems. | [11 empty] | X |  |  |  |  | X
DUCT INSULATION
|  | 23 07 13 | 1.3A | Provide product description, thermal characteristics, list of materials and thickness for each service, and locations. |  |  | X | [8 empty] | X |  |  |  |  | X
|  | 23 07 13 | 1.3B | VOC content for adhesives and sealants | [12 empty] | X |  | X
HVAC PIPING INSULATION
|  | 23 07 19 | 1.4A | For all products; identifying k-value, thickness, jackets, and accessories |  |  | X | [8 empty] | X |  |  |  |  | X
|  | 23 07 19 | 1.4B | VOC content for adhesives and sealants | [12 empty] | X |  | X
COMMISSIONING OF HVAC
|  | 23 08 00 |  | Commissioning submittals | [13 empty] | X |  | X
INSTRUMENTATION AND CONTROL DEVICES FOR HVAC
|  | 23 09 13 | 1.3A | Provide description and engineering data for each control system component, and software module. |  |  | X | [12 empty] | X
|  | 23 09 13 | 1.3B | Include inspection period, cleaning methods, recommended cleaning materials, and calibration tolerances | [11 empty] | X |  | X |  |  | X
|  | 23 09 13 | 1.3C | Certifications and testing supplement to previously submitted O & M manuals | [6 empty] | X | X | [5 empty] | X |  |  | X
REFRIGERATION MONITORING AND CONTROL SYSTEMS (RMCS)
|  | 23 09 16 | 1.3 | Equipment cut sheets for all products, systems, components indicated and installation and user manuals. |  |  | X | [5 empty] | X |  |  | X |  |  |  |  | X
|  | 23 09 16 | 1.3 | Provide drawings showing; components locations in commissary and required wiring between components. |  | X | [9 empty] | X |  |  |  |  | X
|  | 23 09 16 | 1.3 | RMCS Manufacturer's resume | [7 empty] | X | [8 empty] | X
|  | 23 09 16 | 1.3 | Startup technician's resume | [7 empty] | X | [8 empty] | X
|  | 23 09 16 | 1.3 | RMCS Manufacturer's approval of startup technician. | [7 empty] | X | [8 empty] | X
|  | 23 09 16 | 1.3 | Display case/Compressor Manufacturer coordination. | [9 empty] | X | X | [5 empty] | X
|  | 23 09 16 | 1.3 | RMCS Installer qualifications | [7 empty] | X | [8 empty] | X
|  | 23 09 16 | 1.3 | RMCS Manufacturer's approval of startup technician. | [7 empty] | X | [8 empty] | X
REFRIGERATION MONITORING AND CONTROL SYSTEMS (RMCS) MICRO-DISTRIBUTED SYSTEM
|  | 23 09 16 | 1.3 | Equipment cut sheets for all products, systems, components indicated and installation and user manuals. |  |  | X | [5 empty] | X |  |  | X |  |  |  |  | X
|  | 23 09 16 | 1.3 | Provide drawings showing; components locations in commissary and required wiring between components. |  | X | [9 empty] | X |  |  |  |  | X
|  | 23 09 16 | 1.3 | RMCS Manufacturer's resume | [7 empty] | X | [8 empty] | X
|  | 23 09 16 | 1.3 | Startup technician's resume | [7 empty] | X | [8 empty] | X
|  | 23 09 16 | 1.3 | RMCS Manufacturer's approval of startup technician. | [7 empty] | X | [8 empty] | X
|  | 23 09 16 | 1.3 | Display case/Compressor Manufacturer coordination. | [9 empty] | X | X | [5 empty] | X
|  | 23 09 16 | 1.3 | RMCS Installer qualifications | [7 empty] | X | [8 empty] | X
|  | 23 09 16 | 1.3 | RMCS Manufacturer's approval of startup technician. | [7 empty] | X | [8 empty] | X
HYDRONIC PIPING
|  | 23 21 13 | 1.4A | Field test reports | [10 empty] | X | [5 empty] | X
|  | 23 21 13 | 1.4B | VOC content for adhesives and sealants | [12 empty] | X |  | X
HYDRONIC PIPING SPECIALTIES
|  | 23 21 16 | 1.3B | For each product and assembly |  |  | X | [13 empty] | X
|  | 23 21 16 | 1.3C | Pressure vessels | [6 empty] | X | [9 empty] | X
|  | 23 21 16 | 1.3D | Installation Instructions | [8 empty] | X | [7 empty] | X
|  | 23 21 16 | 1.3E | Operation and Maintenance Data | [11 empty] | X |  |  |  |  | X
HVAC PUMPS
|  | 23 22 23 | 1.4B | For each product |  |  | X | [13 empty] | X
|  | 23 22 23 | 1.4C | Installation Instructions | [8 empty] | X | [7 empty] | X
|  | 23 22 23 | 1.4D | Operation and Maintenance Data | [11 empty] | X |  |  |  |  | X
REFRIGERANT PIPING FOR HVAC
|  | 23 23 00 | 1.3B | Indicate schematic layout of system, including equipment, critical dimensions, and sizes developed by the Condensing Unit Manufacturer. |  | X | [14 empty] | X
|  | 23 23 00 | 1.3B | Record actual locations of components. | [10 empty] | X |  |  | X |  |  | X
|  | 23 23 00 | 1.3B | Include operation, maintenance, and inspection data, replacement part numbers and availability, and service depot location and telephone number. | [11 empty] | X |  | X |  |  | X
|  | 23 23 00 | 1.3B | Submit compressor manufacturer warranty and ensure forms have been completed in Owner's name and registered with manufacturer. |  |  |  | X | [9 empty] | X |  |  | X
|  | 23 23 00 | 1.3B | Submit all certifications and testing data as a supplement to previously submitted O & M manuals at contract closeout. | [6 empty] | X | X | [5 empty] | X |  |  | X
WATER TREATMENT FOR CLOSED-LOOP HYDRONIC SYSTEMS
|  | 23 25 13 | 1.3B | For each type |  |  | X | [13 empty] | X
|  | 23 25 13 | 1.3C | Installation Instructions | [8 empty] | X | [7 empty] | X
|  | 23 25 13 | 1.3D | Field Reports | [9 empty] | X | [6 empty] | X
|  | 23 25 13 | 1.3E | Certificate of compliance approving chemicals and their proposed disposal | [7 empty] | X | [8 empty] | X
|  | 23 25 13 | 1.3F | Operation and Maintenance Data | [11 empty] | X |  |  |  |  | X
METAL DUCTS AND AIR ACCESSORIES
|  | 23 31 13 | 1.4A | Indicate pressure tests performed. Include date; section tested, test pressure, and leakage rate, following SMACNA HVAC Air Duct Leakage Test Manual. | [6 empty] | X |  |  |  |  | X |  |  |  |  | X
|  | 23 31 13 | 1.4B | Record actual locations of ducts and duct fittings. Record changes in fitting location and type. Show additional fittings used. | [10 empty] | X |  |  | X |  |  | X
|  | 23 31 13 | 1.4B | Submit all certifications and testing data as a supplement to previously submitted O & M manuals at contract closeout. | [6 empty] | X | X |  |  |  | X |  | X |  |  | X
|  | 23 31 13 | 1.4C | LEED Prerequisites. VOC content for adhesives and sealants |  |  | X |  |  |  | X | [5 empty] | X |  | X
HVAC POWER VENTILATORS
|  | 23 34 23 | 1.3A | Include rated capacities, furnished specialties, and accessories for each type of product indicated |  |  | X | [12 empty] | X
|  | 23 34 23 | 1.3A | For each type product | [8 empty] | X | [6 empty] | X
|  | 23 34 23 | 1.3B | Include manufacturers’ descriptive literature, instructions for lubrication, motor and drive replacement, spare parts list, and wiring diagrams. | [11 empty] | X |  | X |  |  | X
|  | 23 34 23 | 1.3B | Submit all certifications and testing data as a supplement to previously submitted O & M manuals at contract closeout. | [6 empty] | X | X | [5 empty] | X |  |  | X
DIFFUSERS, REGISTERS, AND GRILLES
|  | 23 37 13 | 1.3A | Provide data for equipment required for this project. Include outlets, inlets, size, finish, type of mounting, schedule of outlets. |  |  | X | [8 empty] | X |  |  |  | X
COMMERCIAL-KITCHEN HOODS
|  | 23 38 13 | 1.3B | For each type product |  |  | X | [12 empty] | X
|  | 23 38 13 | 1.3C | Show plans,elevations, sections; indicate performance; attachment; water-supply; control cabinets; fire protection; detail assemblies; diring diagrams. |  | X | [13 empty] | X
|  | 23 38 13 | 1.3D | Piping Diagrams |  | X | [13 empty] | X
|  | 23 38 13 | 1.3E | Field Test reports | [6 empty] | X | [8 empty] | X
|  | 23 38 13 | 1.3F | For each system and product | [11 empty] | X |  |  | X
BREECHINGS, CHIMNEYS, AND STACKS
|  | 23 51 00 | 1.5A | For each type product |  |  | X | [8 empty] | X |  |  |  | X
HEATING BOILERS
|  | 23 52 00 | 1.3B | Provide capacity and dimensions of manufactured products and assemblies required for this project. Indicate electrical service with electrical characteristics and connection requirements, and duct connections. |  |  | X | [12 empty] | X
|  | 23 52 00 | 1.3C | Indicate capacity and dimensions of manufactured products and assemblies required for this project. |  | X | [13 empty] | X
|  | 23 52 00 | 1.3D | For all products | [11 empty] | X |  |  |  | X
|  | 23 52 00 | 1.4A | Indicate condition of equipment after start-up including control settings and performance chart of control system | [8 empty] | X | [5 empty] | X
|  | 23 52 00 | 1.4B | For all products | [11 empty] | X |  | X |  |  | X
|  | 23 52 00 | 1.4C | Submit all certifications and testing data as a supplement to previously submitted O & M manuals at contract closeout. | [6 empty] | X | X | [5 empty] | X |  |  | X
FUEL-FIRED HEATERS
|  | 23 54 16 | 1.3A | Provide manufacturer's literature and data indicating rated capacities, weights, accessories, electrical nameplate data, and wiring diagrams |  |  | X | [12 empty] | X
|  | 23 54 16 | 1.3A | Indicate assembly, required clearances, and locations and sizes of field connections |  | X | [13 empty] | X
|  | 23 54 16 | 1.3A | For all products | [11 empty] | X |  |  |  | X
|  | 23 54 16 | 1.3B | Indicate rigging, assembly, and installation instructions | [8 empty] | X | [5 empty] | X
|  | 23 54 16 | 1.3C | Include manufacturer's descriptive literature, operating instructions, maintenance and repair data, and parts listing | [11 empty] | X |  | X |  |  | X
|  | 23 54 16 | 1.3C | Submit warranty, fill out in government's name and register with manufacturer |  |  |  | X | [9 empty] | X |  |  | X
|  | 23 54 16 | 1.3C | Manufacturer's qualifications | [7 empty] | X | [5 empty] | X |  |  | X
|  | 23 54 16 | 1.3C | Submit all certifications and testing data as a supplement to previously submitted O & M manuals at contract closeout. | [6 empty] | X | X | [5 empty] | X |  |  | X
AIR COOLED CONDENSING UNITS
|  | 23 62 13 | 1.3A | Indicate capacity and dimensions of manufactured products and assemblies required for this project. Indicate electrical service with electrical characteristics and connection requirements, and duct connections. |  | X | [14 empty] | X
|  | 23 62 13 | 1.3A | Provide capacity and dimensions of manufactured products and assemblies required for this project. Indicate electrical service with electrical characteristics and connection requirements, and duct connections. |  |  | X |  |  | X | X |  | X |  |  | X |  |  |  |  | X
|  | 23 62 13 | 1.3B | Include manufacturer's descriptive literature, operating instructions, installation instructions, maintenance and repair instructions, including lubrication instructions, desiccant filter replacement, motor and drive replacement, and spare parts lists. | [11 empty] | X |  | X |  |  | X
|  | 23 62 13 | 1.3B | Recommended Spare Parts List with long and short term requirements | [13 empty] | X |  |  | X
|  | 23 62 13 | 1.3B | Submit all certifications and testing data as a supplement to previously submitted O & M manuals at contract closeout. | [6 empty] | X | X | [5 empty] | X |  |  | X
|  | 23 62 13 | 1.3C | LEED submittals | [12 empty] | X |  | X
PACKAGED WATER CHILLERS
|  | 23 64 00 | 1.3B | Provide manufacturer's literature and data indicating rated capacities, weights, accessories, electrical nameplate data, and wiring diagrams |  |  | X | [12 empty] | X
|  | 23 64 00 | 1.3C | Indicate assembly, required clearances, and locations and sizes of field connections |  | X | [13 empty] | X
|  | 23 64 00 | 1.3C | For all products | [11 empty] | X |  |  |  | X
|  | 23 64 00 | 1.4B | Installation instructions | [8 empty] | X | [5 empty] | X
|  | 23 64 00 | 1.4C | Certify that components of package not furnished by manufacturer have been selected in accordance with manufacturer's requirements | [7 empty] | X | [6 empty] | X
|  | 23 64 00 | 1.5 | Submit all certifications and testing data as a supplement to previously submitted O & M manuals at contract closeout. | [6 empty] | X | X | [5 empty] | X |  |  | X
PACKAGED ROOFTOP HVAC UNITS
|  | 23 74 13 | 1.3A | Indicate capacity and dimensions of manufactured products and assemblies required for this project. Indicate electrical service with electrical characteristics and connection requirements, and duct connections. |  | X | [14 empty] | X
|  | 23 74 13 | 1.3A | Provide capacity and dimensions of manufactured products and assemblies required for this project. Indicate electrical service with electrical characteristics and connection requirements, and duct connections. |  |  | X |  |  | X | X |  | X |  |  | X |  |  |  |  | X
|  | 23 74 13 | 1.3B | Include manufacturer's descriptive literature, operating instructions, installation instructions, maintenance and repair instructions, including lubrication instructions, desiccant filter replacement, motor and drive replacement, and spare parts lists. | [11 empty] | X |  | X |  |  | X
|  | 23 74 13 | 1.3B | Recommended Spare Parts List with long and short term requirements | [13 empty] | X |  |  | X
|  | 23 74 13 | 1.3B | Submit all certifications and testing data as a supplement to previously submitted O & M manuals at contract closeout. | [6 empty] | X | X | [5 empty] | X |  |  | X
|  | 23 74 13 | 1.3C | LEED submittals | [12 empty] | X |  | X
DUCTLESS SPLIT SYSTEM AIR CONDITIONERS
|  | 23 81 26 | 1.3A | Indicate components, assembly, dimensions, weights and loadings, required clearances, and location and size of field connections. Include schematic layouts showing condensing units, cooling coils, refrigerant piping, and accessories required for complete system. |  | X | [13 empty] | X
|  | 23 81 26 | 1.3A | Provide rated capacities, weights, data and wiring diagrams. |  |  | X | [12 empty] | X
CONVECTION HEATING AND COOLING UNITS
|  | 23 82 00 | 1.3A | Include rated capacities, operating characteristics, furnished specialties, and accessories for each type of product indicated |  | X | [14 empty] | X
|  | 23 82 00 | 1.3A | Indicate cross sections of cabinets, grilles, bracing and reinforcing, and typical elevations. Submit schedules of equipment and enclosures typically indicating length and number of pieces of element and enclosure, corner pieces, end caps, cap strips, access doors, pilaster covers, and comparison of specified heat required to actual heat output provided. Indicate mechanical and electrical service locations and requirements. | X | [15 empty] | X
|  | 23 82 00 | 1.3B | Installation instructions and recommendations | [8 empty] | X | [7 empty] | X
|  | 23 82 00 | 1.3C | Record actual locations of components and locations of access doors in radiation cabinets required for access or valving. | [10 empty] | X |  |  |  | X
|  | 23 82 00 | 1.3C | Include manufacturers’ descriptive literature, operating instructions, installation instructions, maintenance and repair data, and parts listings. | [8 empty] | X |  |  | X |  |  | X
|  | 23 82 00 | 1.3C | Submit all certifications and testing data as a supplement to previously submitted O & M manuals | [6 empty] | X | X |  |  |  | X |  | X |  |  | X
AIR COILS
|  | 23 82 16 | 1.3B | Provide coil and frame configurations, dimensions, materials, rows, connections, and rough-in dimensions. |  |  | X | [13 empty] | X
|  | 23 82 16 | 1.3C | Indicate coil and frame configurations, dimensions, capacities, materials, rows, connections, and rough-in dimensions. |  | X | [14 empty] | X
|  | 23 82 16 | 1.3D | Operation and maintenance data | [11 empty] | X |  |  |  |  | X
MECHANICAL DEHUMIDIFICATION UNITS
|  | 23 84 16 | 1.3 | Indicate capacity and dimensions of manufactured products and assemblies required for this project. Indicate electrical service with electrical characteristics and connection requirements, and duct connections. |  | X | X | X | X | X | X | X | X |  |  | X |  | X |  |  | X
PRODUCT REFRIGERATION SYSTEMS
|  | 23 90 00 | 1.3 | Contract variances | [9 empty] | X | [6 empty] | X
|  | 23 90 00 | 1.3 | Refrigeration Capacity Calculations: For each refrigeration system, and for refrigeration piping pressure drops. |  |  | X |  |  | X | [10 empty] | X
|  | 23 90 00 | 1.3 | Provide completed refrigeration schedules in same format as on contract drawings. |  | X | [14 empty] | X
|  | 23 90 00 | 1.3 | Installation drawings including proposed piping, wiring, and equipment; interconnecting piping and wiring between evaporators, unit coolers, heat recovery coils, and refrigerated display cases. Include details for attachment, anchoring, and hanging to structural framing of the building; vibration isolation units; and foundation and supports. |  | X | [14 empty] | X
|  | 23 90 00 | 1.3 | Letter Acknowledging Submitted Design for Electrical | [7 empty] | X | [8 empty] | X
|  | 23 90 00 | 1.3 | Electrical - Provide power layout drawings showing electrical runs with wire sizes, conduit sizes, and connection points. Wiring diagrams shall identify each component, and one diagram shall show interconnected or interlocked components. |  | X | [14 empty] | X
|  | 23 90 00 | 1.3 | Electrical - Breaker Cut Sheets |  |  | X | [13 empty] | X
|  | 23 90 00 | 1.3 | Electrical - Transformer Cut Sheets |  |  | X | [13 empty] | X
|  | 23 90 00 | 1.3 | Subcontract plan |  |  | X | [13 empty] | X
|  | 23 90 00 | 1.3 | Manufacturer data sheets for each product indicated |  |  | X | [5 empty] | X |  |  | X |  |  |  |  | X
|  | 23 90 00 | 1.3 | Manufacturer approval of Installer | [7 empty] | X | [8 empty] | X
|  | 23 90 00 | 1.3 | Installer qualifications | [7 empty] | X | [8 empty] | X
COMMON WORK RESULTS FOR ELECTRICAL
|  | 26 05 00 | 1.2A | For electricity-metering equipment |  |  | X | [13 empty] | X
|  | 26 05 00 | 1.2B | Dimensioned plans and sections or elevation layouts of electricity-metering equipment. |  | X | [14 empty] | X
|  | 26 05 00 | 1.2C | Indicate and interpret test results for compliance with performance requirements. | [6 empty] | X | [9 empty] | X
MEDIUM-VOLTAGE CABLES
|  | 26 05 13 | 1.2A | For each type of product indicated |  |  | X | [13 empty] | X
|  | 26 05 13 | 1.2B | For each type of product indicated |  |  |  |  | X | [11 empty] | X
|  | 26 05 13 | 1.2C | For testing agency, and for cable splicing technician. | [7 empty] | X | [8 empty] | X
|  | 26 05 13 | 1.2D | Source quality-control test reports | [6 empty] | X | [9 empty] | X
|  | 26 05 13 | 1.2E | For each type of product indicated | [7 empty] | X | [8 empty] | X
|  | 26 05 13 | 1.2F | Field quality test reports | [6 empty] | X | [9 empty] | X
LOW-VOLTAGE ELECTRICAL POWER CONDUCTORS AND CABLES
|  | 26 05 19 | 1.2A | For each type of product indicated |  |  | X | [13 empty] | X
|  | 26 05 19 | 1.2B | Field quality test reports | [6 empty] | X | [9 empty] | X
GROUNDING AND BONDING FOR ELECTRICAL SYSTEMS
|  | 26 05 26 | 1.2A | For each type of product indicated |  |  | X | [13 empty] | X
|  | 26 05 26 | 1.3 | For firms and persons listed in "Quality Assurance" paragraph | [7 empty] | X | [8 empty] | X
|  | 26 05 26 | 1.4 | Test reports | [6 empty] | X | [9 empty] | X
RACEWAY AND BOXES FOR ELECTRICAL SYSTEMS
|  | 26 05 33 | 1.3A | For raceways, wireways and fittings, outlet boxes, floor boxes, hinged-cover enclosures, and cabinets. |  |  | X | [12 empty] | X
|  | 26 05 33 | 1.3B | Show fabrication and installation details of components for custom raceways, fittings, boxes, enclosures, and cabinets not completely described by published Product Data. |  | X | [5 empty] | X | [7 empty] | X
|  | 26 05 33 | 1.3C | Signed and sealed by a qualified professional engineer. Include design calculations, detail assemblies, dimensions, weights, loads, required clearances, method of field assembly, components and location and size of each field connection. |  | X | [13 empty] | X
|  | 26 05 33 | 1.3D | Submit certification that enclosures, cabinets, accessories, and components will withstand seismic forces | [7 empty] | X | [7 empty] | X
CABLE TRAYS FOR ELECTRICAL SYSTEMS
|  | 26 05 36 | 1.2A | Include data indicating dimensions and finishes for each type of cable tray indicated. |  |  | X | [12 empty] | X
|  | 26 05 36 | 1.2B | For each type of cable tray. Show fabrication and installation details and seismic restraint details |  | X | [13 empty] | X
|  | 26 05 36 | 1.2C | Coordination drawings |  | X | [13 empty] | X
|  | 26 05 36 | 1.2D | For each type of cable tray, signed by product manufacturer. | [7 empty] | X | [7 empty] | X
|  | 26 05 36 | 1.2E | Manufacturer Seismic Qualification Certification | [7 empty] | X | [7 empty] | X
|  | 26 05 36 | 1.2F | Field Test Reports | [6 empty] | X | [8 empty] | X
|  | 26 05 36 | 1.2G | For cable trays including emergency, operation, and maintenance manuals | [11 empty] | X |  |  |  | X
VIBRATION AND SEISMIC CONTROLS FOR ELECTRICAL SYSTEMS
|  | 26 05 48 | 1.3A | Illustrate and indicate types, styles, materials, strength, fastening provisions, and finish for each type and size of seismic restraint component used. |  |  | X | [12 empty] | X
|  | 26 05 48 | 1.3B | For anchorage and bracing not defined by details and charts on Drawings. Indicate materials, and show designs and calculations signed and sealed by a professional engineer |  | X | [13 empty] | X
|  | 26 05 48 | 1.3C | Coordination Drawings |  | X | [13 empty] | X
|  | 26 05 48 | 1.3D | Signed by manufacturers of seismic restraints certifying that products furnished comply with requirements. | [7 empty] | X
|  | 26 05 48 | 1.3E | For firms and persons listed in "Quality Assurance" paragraph | [7 empty] | X | [7 empty] | X
|  | 26 05 48 | 1.3F | From a qualified testing agency indicating and interpreting test results of seismic control devices for compliance with requirements indicated. | [6 empty] | X | [8 empty] | X
IDENTIFICATION FOR ELECTRICAL SYSTEMS
|  | 26 05 53 | 1.2A | For each electrical identification product |  |  | X | [12 empty] | X
COMMISSIONING OF ELECTRICAL SYSTEMS
|  | 26 08 00 |  | Commissioning submittals | [13 empty] | X |  | X
LIGHTING CONTROL DEVICES
|  | 26 09 23 | 1.2A | For each type of product indicated. |  |  | X | [12 empty] | X
|  | 26 09 23 | 1.2B | Show installation details for occupancy and light-level sensors. |  | X | [13 empty] | X
|  | 26 09 23 | 1.2C | Field quality-control test reports. | [9 empty] | X | [5 empty] | X
|  | 26 09 23 | 1.2D | For each type of product to include in emergency, operation, and maintenance manuals. | [11 empty] | X |  |  |  | X
MEDIUM-VOLTAGE TRANSFORMERS
|  | 26 12 19 | 1.3A | Include rated nameplate data, capacities, weights, dimensions, minimum clearances, installed devices and features, location of each field connection, and performance for each type and size of transformer indicated |  |  | X | [12 empty] | X
|  | 26 12 19 | 1.3B | Wiring and connection diagrams including power, signal and control wiring where applicable |  | X | [13 empty] | X
|  | 26 12 19 | 1.3C | Manufacturer Seismic Qualification Certification | [7 empty] | X | [7 empty] | X
|  | 26 12 19 | 1.3D | Source quality-control test reports | [6 empty] | X
|  | 26 12 19 | 1.3E | Field quality-control test reports | [6 empty] | X | [8 empty] | X
|  | 26 12 19 | 1.3F | Follow-up service reports | [10 empty] | X |  |  |  |  | X
|  | 26 12 19 | 1.3G | For each type | [11 empty] | X |  |  |  | X
LOW-VOLTAGE TRANSFORMERS
|  | 26 22 00 | 1.2A | Include rated nameplate data, capacities, weights, dimensions, minimum clearances, installed devices and features, and performance for each type and size of transformer indicated. |  |  | X | [12 empty] | X
|  | 26 22 00 | 1.2B | Wiring and connection diagrams |  | X | [13 empty] | X
|  | 26 22 00 | 1.2C | Manufacturer Seismic Qualification Certification | [7 empty] | X | [7 empty] | X
|  | 26 22 00 | 1.2D | Source quality-control test reports | [6 empty] | X | [8 empty] | X
|  | 26 22 00 | 1.2E | Output Settings Reports | [6 empty] | X | [8 empty] | X
SWITCHBOARDS
|  | 26 23 00 | 1.3A | For each type of switchboard, overcurrent protective device, surge protective device, ground-fault protector, accessory, and component indicated. Include dimensions and manufacturers' technical data on features, performance, electrical characteristics, ratings, and finishes. |  |  | X | [12 empty] | X
|  | 26 23 00 | 1.3B | For each switchboard and related equipment |  | X | [13 empty] | X
|  | 26 23 00 | 1.3C | Manufacturer Seismic Qualification Certification | [7 empty] | X | [7 empty] | X
|  | 26 23 00 | 1.3D | Field quality-control test reports | [6 empty] | X | [8 empty] | X
|  | 26 23 00 | 1.3E | For switchboards and components to include in emergency, operation, and maintenance manuals | [11 empty] | X |  |  |  | X
PANELBOARDS
|  | 26 24 16 | 1.3A | For each type of panelboard, overcurrent protective device, transient voltage suppression device, accessory, and component indicated. Include dimensions and manufacturers' technical data on features, performance, electrical characteristics, ratings, and finishes. |  |  | X | [12 empty] | X
|  | 26 24 16 | 1.3B | For each panelboard and related equipment. |  | X | [13 empty] | X
|  | 26 24 16 | 1.3C | Manufacturer Seismic Qualification Certification | [7 empty] | X | [7 empty] | X
|  | 26 24 16 | 1.3D | Qualification Data: For testing agency. | [7 empty] | X | [7 empty] | X
|  | 26 24 16 | 1.3E | Field quality-control test reports | [6 empty] | X | [8 empty] | X
|  | 26 24 16 | 1.3F | Panelboard Schedules: For installation in panelboards. Submit final versions after load balancing. |  | X | [6 empty] | X |  | X |  |  |  |  | X
|  | 26 24 16 | 1.3G | For panelboards and components to include in emergency, operation, and maintenance manuals. | [11 empty] | X |  |  |  | X
MOTOR-CONTROL CENTERS
|  | 26 24 19 | 1.2A | For each type |  |  | X | [12 empty] | X
|  | 26 24 19 | 1.2B | LEED Documentation | [12 empty] | X |  | X
|  | 26 24 19 | 1.2C | Include dimensioned plans, elevations, sections, and details, including required clearances and service space around equipment. Show tabulations of installed devices, equipment features, and ratings. |  | X | [13 empty] | X
|  | 26 24 19 | 1.2D | Coordination Drawings |  | X | [13 empty] | X
|  | 26 24 19 | 1.2E | Manufacturer Seismic Qualification Certification | [7 empty] | X | [7 empty] | X
|  | 26 24 19 | 1.2F | Qualification Data: For manufacturer. | [7 empty] | X | [7 empty] | X
|  | 26 24 19 | 1.2G | Field quality-control test reports | [6 empty] | X | [8 empty] | X
|  | 26 24 19 | 1.2H | For each type | [11 empty] | X |  |  |  | X
|  | 26 24 19 | 1.2I | Compile after motors have been installed and arrange to demonstrate that selection of heaters suits actual motor nameplate full-load currents. | [10 empty] | X |  |  |  |  | X
ENCLOSED BUS ASSEMBLIES
|  | 26 25 00 | 1.3A | For each type |  |  | X | [12 empty] | X
|  | 26 25 00 | 1.3B | For each type |  | X | [13 empty] | X
|  | 26 25 00 | 1.3C | For each type | [7 empty] | X | [7 empty] | X
|  | 26 25 00 | 1.3D | Manufacturer Seismic Qualification Certification | [7 empty] | X | [7 empty] | X
|  | 26 25 00 | 1.3E | Field quality-control test reports | [6 empty] | X | [8 empty] | X
|  | 26 25 00 | 1.3F | Operation and Maintenance Data | [11 empty] | X |  |  |  | X
WIRING DEVICES
|  | 26 27 26 | 1.3 | For each type product indicated |  | X | X | [12 empty] | X
PROCESSING AREA SIGNALING (DOORBELL) SYSTEM
|  | 26 27 73 | 1.4 | For each type product indicated |  |  | X | [12 empty] | X
COORDINATED POWER SYSTEM PROTECTION
|  | 26 28 01 | 1.2A | For computer software program to be used for studies |  |  | X | [12 empty] | X
|  | 26 28 01 | 1.2B | Product certificates | [7 empty] | X | [7 empty] | X
|  | 26 28 01 | 1.2C | For coordination-study specialist. | [7 empty] | X | [7 empty] | X
|  | 26 28 01 | 1.2D | Reports | [10 empty] | X |  |  |  |  | X
FUSES
|  | 26 28 13 | 1.2 | For each type fuse indicated |  |  | X | [12 empty] | X
|  | 26 28 13 | 1.2 | Ambient temperature adjustment information |  |  | X |  |  | X |  |  | X | [6 empty] | X
|  | 26 28 13 | 1.2 | For fuses to include in emergency, operation and maintenance manuals | [11 empty] | X |  |  |  | X
ENCLOSED SWITCHES AND CIRCUIT BREAKERS
|  | 26 28 16 | 1.3A | For each type of enclosed switch, circuit breaker, accessory, and component indicated. Include dimensioned elevations, sections, weights, and manufacturers' technical data on features, performance, electrical characteristics, ratings, and finishes. |  |  | X | [12 empty] | X
|  | 26 28 16 | 1.3B | Diagram power, signal, and control wiring |  | X | [13 empty] | X
|  | 26 28 16 | 1.3C | Submit certification that enclosed switches and circuit breakers, accessories, and components will withstand seismic forces defined in Division 26 Section Vibration and Seismic Controls for Electrical Systems | [7 empty] | X | [7 empty] | X
|  | 26 28 16 | 1.3D | Qualificaton data | [7 empty] | X
|  | 26 28 16 | 1.3E | Field quality test reports | [6 empty] | X | [8 empty] | X
|  | 26 28 16 | 1.3F | For enclosed switches and circuit breakers to include in emergency, operation, and maintenance manuals | [11 empty] | X |  |  |  | X
DIESEL-ENGINE DRIVEN GENERATOR SETS
|  | 26 32 14 | 1.3A | Data on features, components, accessories ratings, and performance. Thermal damage curve for generator. Time-current characteristic curves for generator protective device. |  |  | X | [12 empty] | X
|  | 26 32 14 | 1.3B | Detail equipment assemblies and indicate dimensions, weights, loads, required clearances, method of field assembly, components, and location and size of each field connection. |  | X | [13 empty] | X
|  | 26 32 14 | 1.3C | Welding certificates | [7 empty] | X | [7 empty] | X
|  | 26 32 14 | 1.3D | Manufacturer Seismic Qualification Certification | [7 empty] | X
|  | 26 32 14 | 1.3E | Installer and testing agency qualfication data | [7 empty] | X | [7 empty] | X
|  | 26 32 14 | 1.3F | Certified summary of prototype-unit test report. | [6 empty] | X | [8 empty] | X
|  | 26 32 14 | 1.3G | For components and accessories that are equivalent, but not identical, to those tested on prototype unit. | [6 empty] | X | [8 empty] | X
|  | 26 32 14 | 1.3H | Demonstrate compliance with specified requirement to meet performance criteria for sensitive loads. | [6 empty] | X | X | [7 empty] | X
|  | 26 32 14 | 1.3I | Report of factory test on units to be shipped for this Project, showing evidence of compliance with specified requirements. Report of sound generation. Field quality-control test reports. | [6 empty] | X | [8 empty] | X
|  | 26 32 14 | 1.3J | Comply with NFPA 110 | [7 empty] | X | [7 empty] | X
|  | 26 32 14 | 1.3K | For packaged engine generators to include in emergency, operation, and maintenance manuals. | [11 empty] | X |  |  |  | X
|  | 26 32 14 | 1.3L | Warranty |  |  |  | X | [11 empty] | X
POWER FACTOR CORRECTION EQUIPMENT
|  | 26 35 33 | 1.2A | Data on features, components, accessories ratings, and performance. Thermal damage curve for generator. Time-current characteristic curves for generator protective device. |  |  | X | [12 empty] | X
|  | 26 35 33 | 1.2B | Manufacturer Seismic Qualification Certification | [7 empty] | X
|  | 26 35 33 | 1.2C | Indicate and interpret test results for compliance with performance requirements | [6 empty] | X | [8 empty] | X
|  | 26 35 33 | 1.2D | For each type | [11 empty] | X |  |  |  | X
TRANSFER SWITCHES
|  | 26 36 00 | 1.2A | Include rated capacities, operating characteristics, furnished specialties, and accessories. |  |  | X | [12 empty] | X
|  | 26 36 00 | 1.2B | Dimensioned plans, sections, and elevations showing minimum clearances, conductor entry provisions, gutter space, installed features and devices, and material lists for each switch specified. |  | X | [13 empty] | X
|  | 26 36 00 | 1.2C | Manufacturer Seismic Qualification Certification | [7 empty] | X | [7 empty] | X
|  | 26 36 00 | 1.2D | Manufacturer qualification data | [7 empty] | X | [7 empty] | X
|  | 26 36 00 | 1.2E | Field quality-control test reports | [6 empty] | X | [8 empty] | X
|  | 26 36 00 | 1.2F | Operation and Maintenance Data | [11 empty] | X |  |  |  | X
PASSIVE CATHODIC PROTECTION FOR UNDERGROUND AND SUBMERGED PIPING
|  | 26 42 13 | 1.5A | For all types |  |  | X | [12 empty] | X
|  | 26 42 13 | 1.5B | Test reports | [6 empty] | X | [8 empty] | X
|  | 26 42 13 | 1.5C | Operation and Maintenace Data | [11 empty] | X |  |  |  | X
|  | 26 42 13 | 1.5D | Record drawings |  | X | [13 empty] | X
TRANSIENT VOLTAGE SUPPRESSION
|  | 26 43 00 | 1.2A | For each type product |  |  | X | [12 empty] | X
|  | 26 43 00 | 1.2B | Signed by manufacturers of transient voltage suppression devices, certifying that products furnished comply with specified testing and labeling requirements | [7 empty] | X | [7 empty] | X
|  | 26 43 00 | 1.2C | Field test reports | [6 empty] | X | [7 empty] | X
|  | 26 43 00 | 1.2D | Maintenance data for transient voltage suppression devices | [11 empty] | X |  |  |  | X
|  | 26 43 00 | 1.2E | Warranties |  |  |  | X | [10 empty] | X
INTERIOR LIGHTING
|  | 26 51 00 | 1.3A | For each type of lighting fixture scheduled, arranged in order of fixture designation. Include data on features, accessories, finishes, photometric performance data |  |  | X | [12 empty] | X
|  | 26 51 00 | 1.3B | Wiring Diagrams: Power, signal, and control wiring. |  | X | [8 empty] | X |  |  |  |  | X
|  | 26 51 00 | 1.3C | For each type of ballast for dimmer-controlled fixtures, signed by product manufacturer. | [7 empty] | X | [7 empty] | X
|  | 26 51 00 | 1.3D | Field quality-control test reports. | [6 empty] | X | [8 empty] | X
|  | 26 51 00 | 1.3E | For lighting equipment and fixtures to include in emergency, operation, and maintenance manuals. | [11 empty] | X |  |  |  | X
|  | 26 51 00 | 1.3F | Special warranties |  |  |  | X | [11 empty] | X
EXTERIOR LIGHTING
|  | 26 56 00 | 1.3A | For each luminaire including features, accessories and finishes |  |  | X | [12 empty] | X
|  | 26 56 00 | 1.3B | For each pole type; anchor-bolt templates |  | X | X | [12 empty] | X
|  | 26 56 00 | 1.3C | Wiring diagrams |  | X | [13 empty] | X
|  | 26 56 00 | 1.3D | For exterior luminaires; lamps, ballast; finish |  |  |  |  | X | [10 empty] | X
|  | 26 56 00 | 1.3E | Field quality control test reports | [6 empty] | X | [8 empty] | X
|  | 26 56 00 | 1.3F | Operation and Maintenance data | [11 empty] | X |  |  | X
|  | 26 56 00 | 1.3G | Special warranties |  |  |  | X | [10 empty] | X
COMMISSIONING OF COMMUNICATION SYSTEMS
|  | 27 08 00 |  | Commissioning submittals | [13 empty] | X |  | X
COMMUNICATIONS HORIZONTAL CABLING
|  | 27 15 00 | 1.5A | For each type product |  |  | X | [12 empty] | X
|  | 27 15 00 | 1.5B | System labeling schedules; cabling administration drawings; wiring diagrams; cross-connects and patch panels; cable tray layouts |  | X | [13 empty] | X
|  | 27 15 00 | 1.5C | For workstation outlets, jacks, jack assemblies, in specified finish, one for each size and outlet configuration and faceplates for color selection and evaluation of technical features. |  |  |  |  | X | [10 empty] | X
|  | 27 15 00 | 1.5D | For Installer, qualified layout technician, installation supervisor, and field inspector. | [7 empty] | X | [7 empty] | X
|  | 27 15 00 | 1.5E | Source quality reports | [6 empty] | X | [8 empty] | X
|  | 27 15 00 | 1.5F | Field quality reports | [6 empty] | X | [8 empty] | X
|  | 27 15 00 | 1.5G | For splices and connectors | [11 empty] | X |  |  |  | X
|  | 27 15 00 | 1.5H | Software and firmware operational documentation | [11 empty] | X |  |  |  | X
PUBLIC ADDRESS AND MUSIC SYSTEMS
|  | 27 51 16 | 1.3A | For each type product |  |  | X | [12 empty] | X
|  | 27 51 16 | 1.3B | Design calculations, equipment details, control panels, rack arrangements, wiring diagrams |  | X | [13 empty] | X
|  | 27 51 16 | 1.3C | Manufacturer seismic certification; dimensioned outline drawings of equipment; detailed description of equipment anchorage devices | [7 empty] | X | [7 empty] | X
|  | 27 51 16 | 1.3D | Qualification data for installer and testing agency | [7 empty] | X | [6 empty] | X
|  | 27 51 16 | 1.3E | Field quality control test reports | [6 empty] | X | [7 empty] | X
|  | 27 51 16 | 1.3F | Operation and Maintenance Data, including emergency, operation, and maintenance manuals | [11 empty] | X |  |  | X
COMMISSIONING OF ELECTRONIC SAFETY AND SECURITY SYSTEMS
|  | 28 08 00 |  | Commissioning submittals | [13 empty] | X |  | x
INTRUSION DETECTION
|  | 28 16 00 | 1.3A | For each type product |  |  | X | [12 empty] | x
|  | 28 16 00 | 1.3B | Equipment/System description; include methods of operation; type of circuit; sequence of operations and specific descriptions for this project |  |  | X |  |  | X | [9 empty] | X
|  | 28 16 00 | 1.3C | lnstaller qualifications | [7 empty] | X | [6 empty] | X
|  | 28 16 00 | 1.3D | Field quality control test reports | [6 empty] | X | [8 empty] | X
|  | 28 16 00 | 1.3E | Operation and Maintenance data for each type of product, central station control unit hardware and software data. | [14 empty] | X
|  | 28 16 00 | 1.3F | Special warranty specified |  |  |  | X | [10 empty] | X
|  | 28 16 00 | 1.3G | Test Plan and Schedule; Examination reports; anchor inspection reports | [6 empty] | X | [8 empty] | X
VIDEO SURVEILLANCE
|  | 28 23 00 | 1.3A | For each type product |  |  | X | [12 empty] | x
|  | 28 23 00 | 1.3B | Detail assemblies of standard components that are custom assembled for specific application |  | X | [13 empty] | X
|  | 28 23 00 | 1.3C | Include every piece of equipment by model number, manufacturer, serial number, location, and date of original installation. |  |  | X |  |  | X | [8 empty] | X
|  | 28 23 00 | 1.3D | Manufacturer Seismic Qualification Certification | [7 empty] | X | [7 empty] | X
|  | 28 23 00 | 1.3E | Field quality control test reports | [6 empty] | X | [8 empty] | X
|  | 28 23 00 | 1.3F | Operation and Maintenance data for each type of product, central station control unit hardware and software data. | [14 empty] | X
|  | 28 23 00 | 1.3G | Special warranty specified |  |  |  | X | [10 empty] | X
FIRE ALARM / MASS NOTIFICATION SYSTEMS
|  | 28 31 76 | 1.6A | For each type product |  |  | X | [12 empty] | X
|  | 28 31 76 | 1.6B | System operation description; device address list; control input output matrix; system riser diagram; wiring diagrams; batteries; duct smoke detectors; elevation details; device mounting details; floor plans |  | X | [13 empty] | X
|  | 28 31 76 | 1.6C | Cut sheets, calculations and other design documents listed |  | X | [13 empty] | X
|  | 28 31 76 | 1.6D | Copies of certificates for installers and documenting approved manufacture representation shall be provided | [7 empty] | X | [7 empty] | X
|  | 28 31 76 | 1.6E | Field quality-control test reports | [6 empty] | X | [7 empty] | X
|  | 28 31 76 | 1.6F | Operation and Maintenance data | [11 empty] | X |  |  | X
|  | 28 31 76 | 1.6G | Submittals to Authorities Having Jurisdiction | [7 empty] | X | [6 empty] | X
|  | 28 31 76 | 1.6H | "Record of Completion" form and "permanent records documents" | [13 empty] | X |  |  | X
EARTHWORK
|  | 31 00 00 | 1.3A | For each type of plastic warning tape; geotextiles; controlled low strength material; design mixture. |  |  | X | [12 empty] | X
|  | 31 00 00 | 1.3B | Material test reports | [5 empty] | X | X | [7 empty] | X
|  | 31 00 00 | 1.3C | Special Inspection Reports | [6 empty] | X | [8 empty] | X
SITE CLEARING
|  | 31 10 00 | 1.3A | Photographs or Videotape | X | [14 empty] | X
|  | 31 10 00 | 1.3B | Record drawings | X | [9 empty] | X |  |  |  |  | X
|  | 31 10 00 | 1.3C | Erosion and Sedimentation Control Plan | X | [14 empty] | X
TERMITE CONTROL
|  | 31 31 16 | 1.2A | For each type of product |  |  | X | [12 empty] | X
|  | 31 31 16 | 1.2B | For termite control products, from manufacturer | [7 empty] | X | [6 empty] | X
|  | 31 31 16 | 1.2C | Soil Treatment Application Report | [6 empty] | X | [7 empty] | X
|  | 31 31 16 | 1.2D | Warranty | [7 empty] | X | [6 empty] | X
|  | 31 31 16 | 1.2E | Installer qualificaiton | [7 empty] | X | [6 empty] | X
|  | 31 31 16 | 1.2F | Application Confirmation | [6 empty] | X | [7 empty] | X
COMMISSIONING OF EXTERIOR IMPROVEMENTS
|  | 32 08 00 |  | Commissioning submittals | [13 empty] | X |  | X
HOT MIX BITUMINOUS PAVEMENT
|  | 32 12 17 | 1.3A | For each product; including technical data and tested physical and performance properties |  |  | X | [12 empty] | X
|  | 32 12 17 | 1.3B | Job mix designs for each job mix proposed | [5 empty] | X | [9 empty] | X
|  | 32 12 17 | 1.3C | Material test reports | [6 empty] | X | [8 empty] | X
|  | 32 12 17 | 1.3D | Manufacturers qualifications | [7 empty] | X | [7 empty] | X
|  | 32 12 17 | 1.3E | Material certificates | [7 empty] | X | [7 empty] | X
CONCRETE PAVING
|  | 32 13 13 | 1.3A | For each type of product |  |  | X | [12 empty] | X
|  | 32 13 13 | 1.3B | LEED documentation for recycled content and mixtures |  |  | X | [9 empty] | X |  | X
|  | 32 13 13 | 1.3C | Design mixes for each concrete pavement mix | [5 empty] | X | [9 empty] | X
|  | 32 13 13 | 1.3D | Material test reports | [6 empty] | X | [7 empty] | X
CONCRETE PAVING JOINT SEALANTS
|  | 32 13 73 | 1.2A | For each type of product |  |  | X | [12 empty] | X
CHAIN LINK FENCES AND GATES
|  | 32 31 13 | 1.3A | For each type of product |  |  | X | [12 empty] | X
|  | 32 31 13 | 1.3B | Show locations of fence, each gate, posts, rails, and tension wires and details of extended posts, extension arms, gate swing, or other operation, hardware, and accessories. |  | X | [13 empty] | X
|  | 32 31 13 | 1.3C | Certifying that products furnished comply with requirements. | [7 empty] | X | [6 empty] | X
|  | 32 31 13 | 1.3D | Qualification Data | [7 empty] | X | [6 empty] | X
|  | 32 31 13 | 1.3E | Compliance of chain link fence and gate grounding and bonding with performance requirements. | [9 empty] | X |  |  |  |  | X
|  | 32 31 13 | 1.3F | Maintenance Data | [11 empty] | X |  |  | X
PLANTING IRRIGATION
|  | 32 84 00 | 1.4A | For each type |  |  | X | [12 empty] | X
|  | 32 84 00 | 1.4B | Detailed design of the irrigation system piping, including plan layout and locations, types, sizes, capacities, and flow characteristics of sprinkler piping components. |  | X | [13 empty] | X
|  | 32 84 00 | 1.4C | Test reports | [6 empty] | X | [7 empty] | X
|  | 32 84 00 | 1.4D | Operation and Maintenance Data | [11 empty] | X |  |  | X
|  | 32 84 00 | 1.4E | Show each irrigation zone and its control valve |  | X | [12 empty] | X
|  | 32 84 00 | 1.4F | Indicate timing settings for each automatic controller zone. | [5 empty] | X | [8 empty] | X
|  | 32 84 00 | 1.4G | Operation and Maintenance Data | [11 empty] | X |  |  | X
PLANTING
|  | 32 90 00 | 1.2A | Certified analysis for standard products | [7 empty] | X | [6 empty] | X
|  | 32 90 00 | 1.2B | Application instructions | [8 empty] | X | [5 empty] | X
|  | 32 90 00 | 1.2C | For all products |  |  |  |  | X | [9 empty] | X
|  | 32 90 00 | 1.2D | Grass Seed Certification | [7 empty] | X | [6 empty] | X
|  | 32 90 00 | 1.2E | Maintenance Instructions | [11 empty] | X |  |  | X
COMMISSIONING OF UTILITIES
|  | 33 08 00 |  | Commissioning submittals | [13 empty] | X |  | X
WATER DISTRIBUTION
|  | 33 11 00 | 1.4A | For each type |  |  | X | [12 empty] | X
|  | 33 11 00 | 1.4B | Detail precast concrete vault assemblies and indicate dimensions, method of field assembly, and components including wiring diagrams |  | X | [13 empty] | X
|  | 33 11 00 | 1.4C | For piping and specialties including relation to other services in same area, drawn to scale. Show piping and specialty sizes and valves, meter and specialty locations, and elevations. |  | X | [13 empty] | X
|  | 33 11 00 | 1.4D | Purging and Disinfecting Reports | [7 empty] | X | [6 empty] | X
|  | 33 11 00 | 1.4E | Operation and maintenance data | [11 empty] | X |  |  | X
SANITARY SEWERS
|  | 33 30 00 | 1.4A | Product data for piping, fittings, gaskets, couplings, clean-outs, identification materials |  |  | X | [12 empty] | X
|  | 33 30 00 | 1.4B | Precast and cast-in-place concrete manholes, including plan, elevation, sections, details and frames and covers |  | X | [13 empty] | X
|  | 33 30 00 | 1.4C | Design Mix Reports and Calculations | [5 empty] | X | [9 empty] | X
|  | 33 30 00 | 1.4D | Field test reports; include performance compliance requirements | [6 empty] | X | [7 empty] | X
STORM DRAINAGE UTILITIES
|  | 33 40 00 | 1.4A | Product data for piping materials, clean-outs, couplings, identification materials |  |  | X | [12 empty] | X
|  | 33 40 00 | 1.4B | Precast and cast-in-place concrete manholes, including plan, elevation, sections, details and frames and covers |  | X | [13 empty] | X
|  | 33 40 00 | 1.4C | Design Mix Reports and Calculations | [5 empty] | X | [9 empty] | X
|  | 33 40 00 | 1.4D | Field test reports; include performance compliance requirements | [6 empty] | X | [7 empty] | X
NATURAL-GAS DISTRIBUTION
|  | 33 51 00 | 1.4A | Product data for piping, valves, service regulators, service meters |  |  | X | [12 empty] | X
|  | 33 51 00 | 1.4B | For natural gas service piping and service meter assembly. Include plans, elevations, sections, details, and attachments to other work. |  | X | [13 empty] | X
|  | 33 51 00 | 1.4C | Operation and maintenance data | [11 empty] | X |  |  | X
OVERHEAD ELECTRICAL DISTRIBUTION
|  | 33 71 01 | 1.3A | For each type |  |  | X | [12 empty] | X
|  | 33 71 01 | 1.3B | Qualification Data | [7 empty] | X | [7 empty] | X
|  | 33 71 01 | 1.3C | Material certificates | [7 empty] | X | [7 empty] | X
|  | 33 71 01 | 1.3D | Listing documentation | [7 empty] | X | [6 empty] | X
|  | 33 71 01 | 1.3E | Time-Current Coordination Curves | [10 empty] | X |  |  |  |  | X
|  | 33 71 01 | 1.3F | Field Test and Inspection Reports | [6 empty] | X |  |  | X | [5 empty] | X
|  | 33 71 01 | 1.3G | Maintenance Data | [11 empty] | X |  |  | X
UNDERGROUND ELECTRICAL DISTRIBUTION
|  | 33 71 02 | 1.3B | For each type |  |  | X | [12 empty] | X
|  | 33 71 02 | 1.3C | Showing plan and section views of the manholes to scale, detailing wall thicknesses, reinforcement, and layout of ducts, appurtenances and accessories |  | X | [13 empty] | X